# COMPREHENSIVE INTERACTIVE MINIMAP DESIGN DOCUMENT

## FOR LOVABLE.DEV WEB APPLICATION

## EXECUTIVE OVERVIEW

This document outlines the design of an interactive project mindmap that serves as the central command center for the Career Guide Distribution Project. The mindmap provides real-time visibility into all project flows, processes, milestones, and stakeholder activities with clickable nodes that reveal detailed data.

# PART 1: MINIMAP CORE ARCHITECTURE

## 1.1 Visual Layout Options

### Option A: 2D Interactive Mindmap (Recommended)

text

┌─────────────────────────────────────────────────────────────────────────────────────┐

│  🗺️ PROJECT COMMAND CENTER - CAREER GUIDE DISTRIBUTION                    [Live]    │

├─────────────────────────────────────────────────────────────────────────────────────┤

│                                                                                      │

│                              [FIRST RAND GROUP]                                      │

│                         ┌────────────────────────┐                                  │

│                         │     FOUNDATION          │                                  │

│                         │   (Project Sponsor)     │                                  │

│                         └───────────┬────────────┘                                  │

│                                     │                                                │

│         ┌───────────────────────────┼───────────────────────────┐                   │

│         │                           │                           │                   │

│    ┌────▼────┐              ┌───────▼────────┐          ┌───────▼────────┐          │

│    │ PRINT   │              │ 3PL LOGISTICS  │          │   EVENTS &      │          │

│    │ CHINA   │              │   (Sea/Air)    │          │   MARKETING     │          │

│    └────┬────┘              └───────┬────────┘          └───────┬────────┘          │

│         │                           │                           │                   │

│    ┌────┴────┐                ┌─────┴─────┐               ┌─────┴─────┐             │

│    │         │                │           │               │           │             │

│ ┌──▼──┐ ┌───▼───┐       ┌─────▼───┐ ┌───▼────┐    ┌─────▼───┐ ┌───▼────┐          │

│ │ QC   │ │Customs│       │Durban   │ │Cape    │    │Schools  │ │NPO     │          │

│ │      │ │       │       │Port     │ │Town    │    │Delivery │ │Events  │          │

│ └──┬───┘ └───┬───┘       └─────┬───┘ └───┬────┘    └─────┬───┘ └───┬────┘          │

│    │         │                  │         │               │         │               │

│    └─────────┼──────────────────┼─────────┼───────────────┼─────────┘               │

│              │                  │         │               │                         │

│         ┌────▼────┐       ┌─────▼─────┐ ┌▼──────────────┐                         │

│         │WAREHOUSE│       │DISTRIBUTION│ │TRAINING EVENTS│                         │

│         │ NETWORK │       │  NETWORK   │ │  (Teachers)   │                         │

│         └────┬────┘       └─────┬─────┘ └───────────────┘                         │

│              │                  │                                                    │

│         ┌────┴────┐       ┌─────┴─────┐                                             │

│         │         │       │           │                                             │

│      ┌──▼──┐ ┌───▼───┐┌───▼───┐ ┌───▼────┐                                         │

│      │JHB  │ │DBN    ││Cape   │ │PE/EL   │                                         │

│      └──┬───┘ └───┬───┘└───┬───┘ └───┬────┘                                         │

│         └─────────┼────────┼─────────┘                                              │

│                   │        │                                                        │

│            ┌──────▼─────┐ ┌▼────────────────┐                                      │

│            │ LAST MILE  │ │ SPONSOR DASHBOARD│                                      │

│            │ DELIVERY   │ │    [CLICK]       │                                      │

│            └────────────┘ └──────────────────┘                                      │

│                                                                                      │

│  [RISK OVERLAY] [TIMELINE] [REAL-TIME UPDATES] [NOTIFICATIONS]                      │

└─────────────────────────────────────────────────────────────────────────────────────┘

### Option B: 3D Interactive Spherical View (Premium)

- Uses Three.js or A-Frame

- Spherical nodes connected by glowing lines

- Click/drag to rotate view

- Zoom in/out with scroll

- Auto-rotation option

- Color-coded status indicators on nodes

## PART 2: COMPLETE MINIMAP NODE STRUCTURE

## 2.1 Level 1 Nodes (Main Pillars)

### Node 1: CHINA PRODUCTION

yaml

Node ID: production_china

Type: process_node

Status: [in_progress | complete | delayed | on_hold]

Color: #FF6B35

Children:

- content_development

- pre_press_approval

- sample_printing

- bulk_production

- quality_inspection

- packing_palletizing

- export_clearance

Icon: 🏭

KPIs:

- total_sets_produced

- production_completion_percentage

- quality_pass_rate

- days_remaining

### Node 2: INTERNATIONAL LOGISTICS

yaml

Node ID: international_logistics

Type: process_node

Status: [in_progress | complete | delayed | on_hold]

Color: #2E86AB

Children:

- sea_freight_tracking

- air_freight_tracking

- port_arrival

- customs_clearance

- warehousing_receipt

Icon: 🚢

KPIs:

- containers_at_sea

- containers_at_port

- containers_cleared

- containers_in_warehouse

### Node 3: WAREHOUSE NETWORK

yaml

Node ID: warehouse_network

Type: process_node

Status: [in_progress | complete | delayed | on_hold]

Color: #28A745

Children:

- johannesburg_warehouse

- cape_town_warehouse

- durban_warehouse

- polokwane_warehouse

- bloemfontein_warehouse

- kimberley_warehouse

- upington_warehouse

- port_elizabeth_warehouse

- east_london_warehouse

- rustenburg_warehouse

- mbombela_warehouse

- pietermaritzburg_warehouse

- potchefstroom_warehouse

- mahikeng_warehouse

- vredendal_warehouse

Icon: 🏪

### Node 4: DISTRIBUTION NETWORK

yaml

Node ID: distribution_network

Type: process_node

Status: [in_progress | complete | delayed | on_hold]

Color: #FFC107

Children:

- courier_dispatch

- last_mile_delivery

- delivery_confirmation

- real_time_tracking

Icon: 🚚

KPIs:

- schools_reached_today

- sets_delivered_today

- delivery_success_rate

- pending_deliveries

### Node 5: TRAINING & EVENTS

yaml

Node ID: training_events

Type: process_node

Status: [in_progress | complete | delayed | on_hold]

Color: #9B59B6

Children:

- trainer_training

- school_workshops

- teacher_training_events

- district_briefings

- principal_engagement

Icon: 📚

KPIs:

- events_today

- teachers_trained

- attendance_rate

- upcoming_events

### Node 6: FIRST RAND GROUP MARKETING

yaml

Node ID: firstrand_marketing

Type: stakeholder_node

Status: [active | planned | complete]

Color: #E74C3C

Children:

- first_national_bank

- wesbank

- rand_merchant_bank

- firstrand_foundation

- albaraka_bank

- direct_axis

- outsurance

- momentum_metropolitan

- [ALL OPCOs List Below]

Icon: 🏦

### Node 7: NPO MANAGEMENT

yaml

Node ID: npo_management

Type: stakeholder_node

Status: [active | pending | complete]

Color: #17A2B8

Children:

- careerlinx

- edu_npo

- teach_sa

- career_access

- ed_unity

- school_connect

- [ALL NPOs List]

Icon: 🤝

### Node 8: MONITORING & REPORTING

yaml

Node ID: monitoring_reporting

Type: process_node

Status: [active | complete]

Color: #6C757D

Children:

- kpi_tracking

- npo_reporting

- financial_reporting

- impact_assessment

- risk_management

Icon: 📊

## PART 3: COMPLETE FIRST RAND GROUP OPCO LIST

yaml

FirstRandGroup:

parent: FirstRand Limited (JSE: FSR)

subsidiaries:

- First National Bank (FNB):

- FNB South Africa

- FNB Botswana

- FNB Lesotho

- FNB Namibia

- FNB Swaziland

- FNB Mozambique

- FNB Tanzania

- FNB Zambia

- FNB Ghana

- WesBank:

- WesBank Vehicle Finance

- WesBank Asset Finance

- WesBank Insurance

- WesBank Fleet Management

- WesBank Commercial

- Rand Merchant Bank (RMB):

- RMB Corporate Banking

- RMB Investment Banking

- RMB Wealth Management

- RMB Private Equity

- RMB Stockbroking

- FirstRand Foundation:

- Education Programmes

- Enterprise Development

- Social Investment

- Community Development

- Albaraka Bank:

- Islamic Banking

- Shariah Compliant Finance

- Direct Axis:

- Consumer Finance

- Personal Loans

- OUTsurance:

- OUTsurance Car

- OUTsurance Home

- OUTsurance Business

- OUTsurance Life

- Momentum Metropolitan:

- Momentum Health

- Metropolitan Health

- Momentum Wealth

- Metropolitan Financial Planning

- Multiply Wellness

- FirstRand Bank:

- Corporate Banking

- Business Banking

- Private Banking

- FirstRand Merchant Bank:

- Global Markets

- Structured Finance

- Project Finance

- FirstRand Namibia:

- FNB Namibia

- RMB Namibia

- FirstRand Lesotho:

- FNB Lesotho

- FirstRand Swaziland:

- FNB Swaziland

- Ashburton Investments:

- Asset Management

- Unit Trusts

- Private Equity

- Rand Refinery:

- Gold Refining

- Precious Metals

- FirstRand UK:

- London Branch

- FirstRand New York:

- New York Branch

## PART 4: COMPLETE NPO/PBO PARTNER LIST

yaml

NPO_Partners:

- CareerLinx (Primary PBO):

- Contract Value: R12,000,000

- Region: National

- Trainers: 150

- Schools: 2,500

- EduNPO SA:

- Contract Value: R4,500,000

- Region: Gauteng, Western Cape

- Trainers: 45

- Schools: 800

- TeachSA Foundation:

- Contract Value: R3,800,000

- Region: KZN, Eastern Cape

- Trainers: 38

- Schools: 700

- CareerAccess NPO:

- Contract Value: R2,900,000

- Region: Free State, Northern Cape

- Trainers: 25

- Schools: 500

- EdUnity Project:

- Contract Value: R2,100,000

- Region: Limpopo, Mpumalanga

- Trainers: 18

- Schools: 400

- SchoolConnect SA:

- Contract Value: R1,800,000

- Region: North West, Mpumalanga

- Trainers: 15

- Schools: 350

- EduRise NPO:

- Contract Value: R1,200,000

- Region: Rural Clusters

- Trainers: 10

- Schools: 200

- YouthImpact PBO:

- Contract Value: R950,000

- Region: Township Clusters

- Trainers: 8

- Schools: 150

- CommunityEd Network:

- Contract Value: R750,000

- Region: Remote Areas

- Trainers: 6

- Schools: 120

## PART 5: COMPLETE 3PL LOGISTICS PARTNERS

yaml

3PL_Logistics_Partners:

Sea/Air Freight Forwarders:

- DSV SeaFreight:

- China-RSA Routes

- Container Management

- Customs Brokerage

- API: Yes

- DHL Global Forwarding:

- Air Freight (Trainer Consignment)

- Express Shipments

- Customs Clearance

- API: Yes

- M6T Logistics:

- Port to Warehouse

- Container Tracking

- Distribution Management

- API: Yes

- Bidvest International:

- Sea Freight (Bulk)

- Consolidation

- Warehousing

- API: Yes

- Rhenus Logistics:

- Sea/Air Freight

- Project Cargo

- Customs Clearance

- API: Yes

- Stoble Logistics:

- Last-Mile Connectivity

- Regional Distribution

- Inventory Management

- API: Yes

- Transitex Logistics:

- Port Logistics

- Customs Clearance

- Warehousing

- API: Yes

- Value Logistics:

- Supply Chain Management

- Distribution

- Tracking Solutions

- API: Yes

Last-Mile Courier Partners:

- The Courier Guy:

- Urban/Peri-urban

- Same/Next Day

- Coverage: National

- API: Yes

- SLA: 24-48 hours

- Aramex:

- Pan-African Coverage

- International

- Dedicated Couriers

- API: Yes

- SLA: 48-72 hours

- DHL Express:

- Premium Service

- High Value Items

- Guaranteed Delivery

- API: Yes

- SLA: 24 hours

- FedEx:

- Express Delivery

- International

- Tracking

- API: Yes

- SLA: 24-48 hours

- Global Logistics:

- Bulk Freight

- Supply Chain

- Warehousing

- API: Yes

- SLA: 48-72 hours

- Ziyaya Express:

- Rural Delivery

- Remote Areas

- Community Based

- API: In Development

- SLA: 3-5 days

## PART 6: COMMUNICATION & PUSH NOTIFICATION SYSTEM

## 6.1 Twilio Integration Setup

sql

-- =====================================================

-- COMMUNICATION TABLES

-- =====================================================

CREATE TABLE communication_templates (

id UUID PRIMARY KEY DEFAULT gen_random_uuid(),

template_name VARCHAR(100) NOT NULL,

channel VARCHAR(20) CHECK (channel IN ('sms', 'whatsapp', 'email', 'push', 'app_to_app')),

subject VARCHAR(255),

body_template TEXT NOT NULL,

variables JSONB,

created_at TIMESTAMP DEFAULT NOW()

);

CREATE TABLE communication_logs (

id UUID PRIMARY KEY DEFAULT gen_random_uuid(),

recipient_type VARCHAR(50) CHECK (recipient_type IN ('user', 'entity', 'group', 'all')),

recipient_id UUID,

recipient_identifier VARCHAR(255), -- phone, email, device_id

channel VARCHAR(20),

template_id UUID REFERENCES communication_templates(id),

subject VARCHAR(255),

message TEXT,

attachment_urls TEXT[],

status VARCHAR(50) DEFAULT 'pending',

sent_at TIMESTAMP,

delivered_at TIMESTAMP,

read_at TIMESTAMP,

error_message TEXT,

created_at TIMESTAMP DEFAULT NOW()

);

CREATE TABLE notification_subscriptions (

id UUID PRIMARY KEY DEFAULT gen_random_uuid(),

user_id UUID REFERENCES users(id),

event_type VARCHAR(100) NOT NULL,

channel_preferences JSONB,

is_active BOOLEAN DEFAULT TRUE,

created_at TIMESTAMP DEFAULT NOW()

);

## 6.2 Communication Flow Triggers

yaml

Push Notification Triggers:

Production Events:

- trigger: batch_production_started

channels: [sms, email, push]

recipients: [project_manager, procurement, sponsor_admin]

template: |

🏭 BATCH {batch_number} PRODUCTION STARTED

Sets: {set_quantity}

ETA Completion: {completion_date}

Quality Inspection: {inspection_schedule}

- trigger: quality_inspection_passed

channels: [email, push, whatsapp]

recipients: [project_manager, logistics_coordinator]

template: |

✅ QUALITY INSPECTION PASSED

Batch: {batch_number}

Defect Rate: {defect_rate}% (Target: <2%)

Shipment Clearance: Approved

- trigger: production_delay_detected

channels: [sms, email, push]

recipients: [project_manager, sponsor_admin, head_of_operations]

template: |

⚠️ PRODUCTION DELAY DETECTED

Batch: {batch_number}

Delay: {delay_days} days

Reason: {delay_reason}

Backup Plan: {backup_plan}

Shipping Events:

- trigger: container_loaded

channels: [email, push]

recipients: [logistics_team, warehouse_managers]

template: |

📦 CONTAINER {container_id} LOADED

Vessel: {vessel_name}

ETA Port: {eta_port}

Tracking: {tracking_number}

- trigger: vessel_departed

channels: [sms, email, push]

recipients: [project_manager, sponsor_admin]

template: |

🚢 VESSEL {vessel_name} DEPARTED

From: {port_origin}

To: {port_destination}

Transit: {transit_days} days

Tracking: {tracking_url}

- trigger: daily_position_update (every 3 hours)

channels: [push]

recipients: [logistics_team]

template: |

📍 POSITION UPDATE - {vessel_name}

Time: {current_time}

Latitude: {latitude}

Longitude: {longitude}

Speed: {speed} knots

ETA: {remaining_days} days

- trigger: vessel_near_port (within 100nm)

channels: [sms, email, push]

recipients: [logistics_team, customs_broker, warehouse_managers]

template: |

🔔 VESSEL APPROACHING PORT

Vessel: {vessel_name}

Port: {port_name}

ETA: {eta} hours

Status: {status}

Action Required: Prepare documentation

Customs Events:

- trigger: cargo_arrived_port

channels: [sms, email, push]

recipients: [logistics_team, customs_broker, project_manager]

template: |

📥 CARGO ARRIVED AT PORT

Port: {port_name}

Container: {container_id}

Customs Clearance: Initiated

ETA Release: {estimated_release}

- trigger: customs_clearance_complete

channels: [sms, email, push]

recipients: [logistics_team, warehouse_managers, project_manager, sponsor_admin]

template: |

✅ CUSTOMS CLEARANCE COMPLETE

Container: {container_id}

Duty Paid: {duty_amount}

VAT Paid: {vat_amount}

Release: {release_date}

Transport to Warehouse: Scheduled

Warehouse Events:

- trigger: goods_received_warehouse

channels: [sms, email, push]

recipients: [warehouse_manager, logistics_team, project_manager]

template: |

📦 GOODS RECEIVED

Warehouse: {warehouse_name}

Location: {warehouse_location}

Sets Received: {sets_received}

Stock Level: {stock_level}

Status: Verified

- trigger: stock_level_threshold (below 10%)

channels: [sms, email, push]

recipients: [warehouse_manager, logistics_team, project_manager]

template: |

⚠️ STOCK ALERT

Warehouse: {warehouse_name}

Current Stock: {stock_level} sets

Threshold: {threshold}%

Action: Re-order required

- trigger: inter_warehouse_transfer_started

channels: [email, push]

recipients: [source_warehouse, destination_warehouse, logistics_team]

template: |

🔄 WAREHOUSE TRANSFER

Source: {source_warehouse}

Destination: {destination_warehouse}

Quantity: {quantity} sets

Courier: {courier}

ETA: {eta}

Delivery Events:

- trigger: delivery_scheduled

channels: [sms, email, push]

recipients: [school_principal, npo_organizer, courier]

template: |

📦 DELIVERY SCHEDULED

School: {school_name}

Address: {school_address}

Date: {delivery_date}

Time: {delivery_time}

Courier: {courier_name}

Tracking: {tracking_link}

- trigger: courier_picked_up

channels: [sms, push]

recipients: [school_principal, logistics_team]

template: |

✅ ORDER PICKED UP

Courier: {courier_name}

Tracking: {tracking_number}

ETA: {estimated_delivery}

- trigger: delivery_in_transit

channels: [push] (every 2 hours)

recipients: [school_principal, sponsor_viewer]

template: |

🚚 DELIVERY IN TRANSIT

Current Location: {current_location}

Next Stop: {next_stop}

Remaining: {remaining_stops} stops

Updated ETA: {eta}

- trigger: delivery_out_for_delivery

channels: [sms, push]

recipients: [school_principal, npo_organizer]

template: |

🚚 DELIVERY OUT FOR DELIVERY

Courier: {courier_name}

Driver: {driver_name}

Phone: {driver_phone}

Arriving: {eta_minutes} minutes

- trigger: delivery_completed

channels: [sms, email, push, whatsapp]

recipients: [school_principal, npo_organizer, sponsor_admin, project_manager]

template: |

✅ DELIVERY COMPLETED

School: {school_name}

Sets Delivered: {sets_delivered}

Time: {delivery_time}

Recipient: {recipient_name}

POD: {pod_link}

Thank you! School coverage: {coverage_percentage}%

- trigger: delivery_failed

channels: [sms, email, push]

recipients: [logistics_team, npo_organizer, project_manager]

template: |

❌ DELIVERY ATTEMPT FAILED

School: {school_name}

Reason: {failure_reason}

Next Attempt: {next_attempt}

Action Required: {action_required}

Training Events:

- trigger: event_reminder_48h

channels: [sms, email, push, whatsapp]

recipients: [attendees, trainers, npo_organizer, dbe_official]

template: |

📅 EVENT REMINDER (48 Hours)

Event: {event_name}

Date: {event_date}

Time: {event_time}

Venue: {venue_name}

Address: {venue_address}

Attending: {attending_count} teachers

Map: {maps_link}

- trigger: event_reminder_24h

channels: [sms, email, push, whatsapp]

recipients: [attendees, trainers, npo_organizer]

template: |

🔔 EVENT TOMORROW

Event: {event_name}

Time: {event_time}

Venue: {venue_name}

Don't forget to bring: {items_to_bring}

- trigger: event_reminder_1h

channels: [sms, push]

recipients: [attendees, trainers, npo_organizer, dbe_official]

template: |

⏰ EVENT STARTS IN 1 HOUR

Event: {event_name}

Time: {event_time}

Venue: {venue_name}

Registration: Opens at {registration_time}

- trigger: event_started

channels: [push, whatsapp]

recipients: [npo_organizer, project_manager, sponsor_viewer]

template: |

🎯 EVENT STARTED

Event: {event_name}

Venue: {venue_name}

Attendees Present: {present_count}/{expected_count}

Photos: {photo_link}

- trigger: event_completed

channels: [sms, email, push]

recipients: [npo_organizer, project_manager, sponsor_admin]

template: |

✅ EVENT COMPLETED

Event: {event_name}

Attendees: {attendees} teachers

Feedback Score: {feedback_score}/5

Report: {report_link}

Photos: {photo_gallery}

Risk/Milestone Events:

- trigger: milestone_achieved

channels: [email, push]

recipients: [project_manager, sponsor_admin, all_stakeholders]

template: |

🎉 MILESTONE ACHIEVED

Milestone: {milestone_name}

Target Date: {target_date}

Achieved: {achieved_date}

Progress: {completion_percentage}%

Next Milestone: {next_milestone}

- trigger: milestone_delayed

channels: [sms, email, push]

recipients: [project_manager, sponsor_admin, ops_manager]

template: |

⚠️ MILESTONE DELAYED

Milestone: {milestone_name}

Original Date: {original_date}

New Date: {new_date}

Delay: {delay_days} days

Reason: {delay_reason}

Recovery Plan: {recovery_plan}

Impact: {impact_assessment}

- trigger: critical_path_risk_detected

channels: [sms, email, push]

recipients: [project_manager, sponsor_admin, CEO]

template: |

🚨 CRITICAL PATH RISK DETECTED

Risk ID: {risk_id}

Description: {risk_description}

Impact: {impact_level}

Probability: {probability}

Mitigation: {mitigation_plan}

Response Required: {response_deadline}

- trigger: risk_mitigation_activated

channels: [sms, email, push]

recipients: [project_manager, ops_manager, relevant_team]

template: |

⚡ RISK MITIGATION ACTIVATED

Risk: {risk_name}

Action: {mitigation_action}

Activated: {activation_time}

Status: {status}

Team Lead: {team_lead}

Contact: {contact_phone}

## PART 7: REAL-TIME DATA INTEGRATION FLOWS

## 7.1 Data Flow Architecture

text

┌──────────────────────────────────────────────────────────────────────────────────┐

│                       REAL-TIME DATA INTEGRATION LAYER                          │

├──────────────────────────────────────────────────────────────────────────────────┤

│                                                                                   │

│  ┌─────────────────────────────────────────────────────────────────────────────┐ │

│  │                     DATA SOURCE LAYER                                        │ │

│  │                                                                              │ │

│  │  ┌──────────────┐  ┌──────────────┐  ┌──────────────┐  ┌──────────────┐    │ │

│  │  │  Printer     │  │  Shipping    │  │  Customs     │  │  Courier     │    │ │

│  │  │  Systems     │  │  Tracking    │  │  Systems     │  │  Systems     │    │ │

│  │  │  (China)     │  │  (AIS/GPS)   │  │  (SARS)      │  │  (API)       │    │ │

│  │  └──────┬───────┘  └──────┬───────┘  └──────┬───────┘  └──────┬───────┘    │ │

│  └─────────┼─────────────────┼─────────────────┼─────────────────┼────────────┘ │

│            │                 │                 │                 │               │

│            ▼                 ▼                 ▼                 ▼               │

│  ┌─────────────────────────────────────────────────────────────────────────────┐ │

│  │                     DATA INGESTION LAYER                                    │ │

│  │                                                                              │ │

│  │  ┌──────────────┐  ┌──────────────┐  ┌──────────────┐  ┌──────────────┐    │ │

│  │  │ Webhooks     │  │ API Polling  │  │ File Imports │  │ Manual Entry │    │ │

│  │  │ (Real-time)  │  │ (Every 30s)  │  │ (CSV/Excel)  │  │ (Fallback)   │    │ │

│  │  └──────┬───────┘  └──────┬───────┘  └──────┬───────┘  └──────┬───────┘    │ │

│  └─────────┼─────────────────┼─────────────────┼─────────────────┼────────────┘ │

│            │                 │                 │                 │               │

│            ▼                 ▼                 ▼                 ▼               │

│  ┌─────────────────────────────────────────────────────────────────────────────┐ │

│  │                     PROCESSING LAYER                                        │ │

│  │                                                                              │ │

│  │  ┌────────────────────────────────────────────────────────────────────────┐ │ │

│  │  │  Supabase Real-time / PostgreSQL + TimescaleDB + PostGIS              │ │ │

│  │  ├────────────────────────────────────────────────────────────────────────┤ │ │

│  │  │  - Data Validation & Transformation                                   │ │ │

│  │  │  - Geocoding & Spatial Indexing                                       │ │ │

│  │  │  - Aggregation & Analytics                                            │ │ │

│  │  │  - Event Detection & Trigger Management                               │ │ │

│  │  │  - Audit Trail & Versioning                                           │ │ │

│  │  └────────────────────────────────────────────────────────────────────────┘ │ │

│  └─────────────────────────────────────────────────────────────────────────────┘ │

│                                                                                   │

│  ┌─────────────────────────────────────────────────────────────────────────────┐ │

│  │                     DELIVERY LAYER                                           │ │

│  │                                                                              │ │

│  │  ┌──────────────┐  ┌──────────────┐  ┌──────────────┐  ┌──────────────┐    │ │

│  │  │ Web Portal   │  │ Mobile App   │  │ Twilio Push  │  │ Third-Party  │    │ │

│  │  │ (Dashboard)  │  │ (Couriers)   │  │ Notifications│  │ Integrations │    │ │

│  │  └──────────────┘  └──────────────┘  └──────────────┘  └──────────────┘    │ │

│  └─────────────────────────────────────────────────────────────────────────────┘ │

│                                                                                   │

└──────────────────────────────────────────────────────────────────────────────────┘

## 7.2 3-Hour Update Cycle Schedule

yaml

Real-time Update Schedule (Every 3 Hours):

00:00 - Vessel position update

03:00 - Port arrival status update

06:00 - Customs clearance status update

09:00 - Warehouse stock level update

12:00 - Mid-day delivery status update

15:00 - Courier GPS position update

18:00 - Training event progress update

21:00 - Daily summary & KPI update

Critical Event Triggers (Instant):

- Vessel position when < 50nm from port

- Customs clearance release

- Emergency/delay detection

- Major milestone completion

- Critical risk escalation

## PART 8: INTERACTIVE MINIMAP NODE DETAILS

## 8.1 Node Click Behaviors

### Example: Clicking "Warehouse Network" Node

text

┌─────────────────────────────────────────────────────────────────────────────────────┐

│  🏪 WAREHOUSE NETWORK                                                   [Close]    │

├─────────────────────────────────────────────────────────────────────────────────────┤

│                                                                                      │

│  ┌─────────────────────────────────────────────────────────────────────────────────┐ │

│  │  Summary Stats                                                                  │ │

│  │  ┌─────────────┐ ┌─────────────┐ ┌─────────────┐ ┌─────────────┐              │ │

│  │  │ Total Stock  │ │ Distributed │ │ Pending     │ │ Storage Used│              │ │

│  │  │ 18,500 sets  │ │ 12,300 sets │ │ 6,200 sets  │ │ 42%         │              │ │

│  │  └─────────────┘ └─────────────┘ └─────────────┘ └─────────────┘              │ │

│  └─────────────────────────────────────────────────────────────────────────────────┘ │

│                                                                                      │

│  ┌─────────────────────────────────────────────────────────────────────────────────┐ │

│  │  Warehouse List                                     [Expand All] [Refresh]     │ │

│  │  ┌─────────────────────────────────────────────────────────────────────────────┐ │ │

│  │  │  ┌─────────────────────────────────────────────────────────────────────────┐ │ │

│  │  │  │  📍 Johannesburg (Primary - Tier 1)                           [CLICK]  │ │ │

│  │  │  │  Stock: 5,200 sets | Capacity: 15,000 | Status: 🟢 Operational         │ │ │

│  │  │  │  Receiving: 3 containers | Dispatch: 45 deliveries today                │ │ │

│  │  │  │  Manager: Mr. J. Botha | Phone: 011 345 6789                           │ │ │

│  │  │  └─────────────────────────────────────────────────────────────────────────┘ │ │

│  │  │  ┌─────────────────────────────────────────────────────────────────────────┐ │ │

│  │  │  │  📍 Cape Town (Secondary - Tier 2)                            [CLICK]  │ │ │

│  │  │  │  Stock: 3,800 sets | Capacity: 10,000 | Status: 🟢 Operational         │ │ │

│  │  │  │  Receiving: 2 containers | Dispatch: 32 deliveries today                │ │ │

│  │  │  │  Manager: Ms. S. Mbeki | Phone: 021 456 7890                           │ │ │

│  │  │  └─────────────────────────────────────────────────────────────────────────┘ │ │

│  │  │  ┌─────────────────────────────────────────────────────────────────────────┐ │ │

│  │  │  │  📍 Durban (Secondary - Tier 2)                               [CLICK]  │ │ │

│  │  │  │  Stock: 2,900 sets | Capacity: 8,000 | Status: 🟡 Operational          │ │ │

│  │  │  │  ⚠️ Low stock alert | Receiving: 0 containers | Dispatch: 28 deliveries │ │ │

│  │  │  │  Manager: Mr. K. Naidoo | Phone: 031 567 8901                           │ │ │

│  │  │  └─────────────────────────────────────────────────────────────────────────┘ │ │

│  │  │  [...] More warehouses                                                     │ │ │

│  │  └─────────────────────────────────────────────────────────────────────────────┘ │ │

│  └─────────────────────────────────────────────────────────────────────────────────┘ │

│                                                                                      │

│  ┌─────────────────────────────────────────────────────────────────────────────────┐ │

│  │  Warehouse Network Map                                                          │ │

│  │  ┌───────────────────────────────────────────────────────────────────────────┐  │ │

│  │  │                    [South Africa Map with Warehouse Pins]                  │  │ │

│  │  │                                                                           │  │ │

│  │  │  🏪 JHB  │  🏪 PTA  │  🏪 POL  │  🏪 BFN  │  🏪 KIM  │  🏪 UPT         │  │ │

│  │  │  🏪 DBN  │  🏪 PE   │  🏪 EL   │  🏪 RUS  │  🏪 MBH  │  🏪 PMB         │  │ │

│  │  │  🏪 CPT  │  🏪 VRD  │  🏪 POT  │  🏪 MAH  │         │                 │  │ │

│  │  └───────────────────────────────────────────────────────────────────────────┘  │ │

│  └─────────────────────────────────────────────────────────────────────────────────┘ │

│                                                                                      │

└─────────────────────────────────────────────────────────────────────────────────────┘

### Example: Clicking "First Rand Group Marketing" Node

text

┌─────────────────────────────────────────────────────────────────────────────────────┐

│  🏦 FIRST RAND GROUP MARKETING                                           [Close]    │

├─────────────────────────────────────────────────────────────────────────────────────┤

│                                                                                      │

│  ┌─────────────────────────────────────────────────────────────────────────────────┐ │

│  │  Group Entity Selection                                                         │ │

│  │  ┌─────────────────────────────────────────────────────────────────────────────┐ │ │

│  │  │  [FNB] [WesBank] [RMB] [FirstRand Foundation] [OUTsurance] [Momentum] [All] │ │ │

│  │  └─────────────────────────────────────────────────────────────────────────────┘ │ │

│  └─────────────────────────────────────────────────────────────────────────────────┘ │

│                                                                                      │

│  ┌─────────────────────────────────────────────────────────────────────────────────┐ │

│  │  Active Campaigns & Events                                                      │ │

│  │  ┌─────────────────────────────────────────────────────────────────────────────┐ │ │

│  │  │  WESBANK - Career Guide Brand Activation                                    │ │ │

│  │  │  ┌─────────────────────────────────────────────────────────────────────────┐ │ │

│  │  │  │  Event: 2025-03-15 | Soweto Thusong Centre | 08:00-15:00               │ │ │

│  │  │  │  NPO: CareerLinx | Trainers: 12 | Teachers: 150 expected                │ │ │

│  │  │  │  Schools: 25 | UCG Sets: 625                                           │ │ │

│  │  │  │  Marketing Stand: ☑ Setup | ☑ Materials | ☑ Staff                      │ │ │

│  │  │  │  VIP: DBE Director - Region 3 | WesBank Marketing Manager              │ │ │

│  │  │  │  Photos: [Gallery] | Videos: [Media]                                   │ │ │

│  │  │  │  Social Media: [Facebook] [Twitter/X] [Instagram] [LinkedIn]           │ │ │

│  │  │  │  Hashtags: #WesBankCareers #CareerGuideSA #FutureReady                │ │ │

│  │  │  └─────────────────────────────────────────────────────────────────────────┘ │ │

│  │  └─────────────────────────────────────────────────────────────────────────────┘ │ │

│  │  ┌─────────────────────────────────────────────────────────────────────────────┐ │ │

│  │  │  FNB - Teacher Training Partnership                                         │ │ │

│  │  │  ┌─────────────────────────────────────────────────────────────────────────┐ │ │

│  │  │  │  Event: 2025-03-18 | Cape Town Civic Centre | 09:00-16:00              │ │ │

│  │  │  │  NPO: TeachSA | Trainers: 8 | Teachers: 100 expected                    │ │ │

│  │  │  │  Schools: 20 | UCG Sets: 500                                           │ │ │

│  │  │  │  Marketing: FNB Kiosk | Branded Materials | Digital Content             │ │ │

│  │  │  └─────────────────────────────────────────────────────────────────────────┘ │ │

│  │  └─────────────────────────────────────────────────────────────────────────────┘ │ │

│  └─────────────────────────────────────────────────────────────────────────────────┘ │

│                                                                                      │

│  ┌─────────────────────────────────────────────────────────────────────────────────┐ │

│  │  Media & Social Impact                                                          │ │

│  │  ┌─────────────────────────────────────────────────────────────────────────────┐ │ │

│  │  │  Reach: 850,000 | Impressions: 2.1M | Engagement: 4.2%                     │ │ │

│  │  │  Top Posts:                                                                 │ │ │

│  │  │  • Career Guide Launch - 45,000 engagements                                │ │ │

│  │  │  • Teacher Training in Soweto - 32,000 engagements                         │ │ │

│  │  │  • WesBank Career Journey - 28,000 engagements                             │ │ │

│  │  │  [Share] [Schedule] [Analytics] [Boost]                                    │ │ │

│  │  └─────────────────────────────────────────────────────────────────────────────┘ │ │

│  └─────────────────────────────────────────────────────────────────────────────────┘ │

│                                                                                      │

└─────────────────────────────────────────────────────────────────────────────────────┘

### Example: Clicking "Delivery Schedule" Node

text

┌─────────────────────────────────────────────────────────────────────────────────────┐

│  📋 TODAY'S DELIVERY SCHEDULE                                             [Close]    │

├─────────────────────────────────────────────────────────────────────────────────────┤

│                                                                                      │

│  ┌─────────────────────────────────────────────────────────────────────────────────┐ │

│  │  Date: 2025-03-15 | Status: 🟢 45/47 Completed | ⏰ 2 Pending                  │ │

│  └─────────────────────────────────────────────────────────────────────────────────┘ │

│                                                                                      │

│  ┌─────────────────────────────────────────────────────────────────────────────────┐ │

│  │  Province Filter: [Gauteng] [Western Cape] [KZN] [All]                         │ │

│  └─────────────────────────────────────────────────────────────────────────────────┘ │

│                                                                                      │

│  ┌─────────────────────────────────────────────────────────────────────────────────┐ │

│  │  GAUTENG (18 schools)                                             [Expand All]  │ │

│  │  ┌─────────────────────────────────────────────────────────────────────────────┐ │ │

│  │  │  ┌─────────────────────────────────────────────────────────────────────────┐ │ │

│  │  │  │  ✅ Parktown High School - Delivered 08:32                              │ │ │

│  │  │  │  Sets: 25 | Courier: Courier Guy | POD: [View]                         │ │ │

│  │  │  └─────────────────────────────────────────────────────────────────────────┘ │ │

│  │  │  ┌─────────────────────────────────────────────────────────────────────────┐ │ │

│  │  │  │  ✅ Soweto Primary School - Delivered 09:15                            │ │ │

│  │  │  │  Sets: 50 | Courier: Aramex | Recipient: Principal N. Khumalo          │ │ │

│  │  │  │  GPS: -26.2488, 27.8589 | Photo: [View]                                │ │ │

│  │  │  └─────────────────────────────────────────────────────────────────────────┘ │ │

│  │  │  ┌─────────────────────────────────────────────────────────────────────────┐ │ │

│  │  │  │  🟡 Diepkloof Secondary School - In Transit (9:30 ETA)                 │ │ │

│  │  │  │  Sets: 35 | Courier: DHL Express | Driver: J. Molefe                  │ │ │

│  │  │  │  Location: 5 km away | ETA: 12 min                                    │ │ │

│  │  │  │  [Track Live] [Call Driver]                                            │ │ │

│  │  │  └─────────────────────────────────────────────────────────────────────────┘ │ │

│  │  └─────────────────────────────────────────────────────────────────────────────┘ │ │

│  └─────────────────────────────────────────────────────────────────────────────────┘ │

│                                                                                      │

│  ┌─────────────────────────────────────────────────────────────────────────────────┐ │

│  │  WESTERN CAPE (12 schools)                                          [Expand]    │ │

│  └─────────────────────────────────────────────────────────────────────────────────┘ │

│                                                                                      │

│  ┌─────────────────────────────────────────────────────────────────────────────────┐ │

│  │  KWAZULU-NATAL (17 schools)                                          [Expand]   │ │

│  └─────────────────────────────────────────────────────────────────────────────────┘ │

│                                                                                      │

└─────────────────────────────────────────────────────────────────────────────────────┘

## PART 9: RISK MANAGEMENT OVERLAY

## 9.1 Risk Visualization on Mindmap

text

┌─────────────────────────────────────────────────────────────────────────────────────┐

│  ⚠️ RISK OVERLAY ACTIVE                                                  [Disable]  │

├─────────────────────────────────────────────────────────────────────────────────────┤

│                                                                                      │

│  ┌─────────────────────────────────────────────────────────────────────────────────┐ │

│  │  Current Risks by Node                                                         │ │

│  │                                                                                  │ │

│  │  ┌─────────────────────────────────────────────────────────────────────────────┐ │ │

│  │  │  🔴 CRITICAL                                                                 │ │ │

│  │  │  • Production Delay - Delay: 5 days | Impact: High | Probability: High      │ │ │

│  │  │    Mitigation: Expedited shipping, backup manufacturer identified           │ │ │

│  │  │    Action: PM to approve overtime, escalate to China liaison                │ │ │

│  │  │    Owner: Procurement Manager | Deadline: 2025-03-17                        │ │ │

│  │  │    [Update] [Escalate] [Acknowledge] [Close]                                │ │ │

│  │  └─────────────────────────────────────────────────────────────────────────────┘ │ │

│  │                                                                                  │ │

│  │  ┌─────────────────────────────────────────────────────────────────────────────┐ │ │

│  │  │  🟡 HIGH                                                                     │ │ │

│  │  │  • Customs Clearance Delay - Additional documentation required              │ │ │

│  │  │    Impact: Medium | Probability: Medium                                    │ │ │

│  │  │    Mitigation: Customs broker on standby, pre-clearance submitted           │ │ │

│  │  │    Owner: Logistics Coordinator | Deadline: 2025-03-18                      │ │ │

│  │  │    [Update] [Acknowledge]                                                   │ │ │

│  │  └─────────────────────────────────────────────────────────────────────────────┘ │ │

│  │                                                                                  │ │

│  │  ┌─────────────────────────────────────────────────────────────────────────────┐ │ │

│  │  │  🟡 HIGH                                                                     │ │ │

│  │  │  • Warehouse Stock Alert - Durban below 10% threshold                       │ │ │

│  │  │    Impact: Medium | Probability: Medium                                    │ │ │

│  │  │    Mitigation: Inter-warehouse transfer from JHB scheduled                  │ │ │

│  │  │    Owner: Warehouse Manager | Deadline: 2025-03-16                          │ │ │

│  │  │    [Update] [Acknowledge]                                                   │ │ │

│  │  └─────────────────────────────────────────────────────────────────────────────┘ │ │

│  │                                                                                  │ │

│  │  ┌─────────────────────────────────────────────────────────────────────────────┐ │ │

│  │  │  🟢 MEDIUM (3 risks)                                           [Expand]    │ │ │

│  │  └─────────────────────────────────────────────────────────────────────────────┘ │ │

│  │                                                                                  │ │

│  │  ┌─────────────────────────────────────────────────────────────────────────────┐ │ │

│  │  │  🟢 LOW (5 risks)                                              [Expand]    │ │ │

│  │  └─────────────────────────────────────────────────────────────────────────────┘ │ │

│  └─────────────────────────────────────────────────────────────────────────────────┘ │

│                                                                                      │

│  ┌─────────────────────────────────────────────────────────────────────────────────┐ │

│  │  Risk Timeline                                                                  │ │

│  │  ┌─────────────────────────────────────────────────────────────────────────────┐ │ │

│  │  │  Today: 🔴 Critical | 🟡 2 High | 🟢 3 Medium | 🟢 5 Low                   │ │ │

│  │  │  Tomorrow: 🔴 Critical | 🟡 1 High | 🟢 4 Medium | 🟢 3 Low                │ │ │

│  │  │  Week Ahead: 🟡 3 High | 🟢 4 Medium | 🟢 2 Low                            │ │ │

│  │  │  [View Full Risk Register] [Generate Risk Report]                           │ │ │

│  │  └─────────────────────────────────────────────────────────────────────────────┘ │ │

│  └─────────────────────────────────────────────────────────────────────────────────┘ │

│                                                                                      │

└─────────────────────────────────────────────────────────────────────────────────────┘

## 9.2 Risk Mitigation Recovery Flow

yaml

Recovery Workflow for Critical Delay:

Trigger: Production Delay Detected

Detection: Daily production report vs schedule

Escalation: Immediate to PM and Ops Manager

Step 1 - Root Cause Analysis:

- Current Production Rate: X units/day

- Required Rate: Y units/day

- Gap: Z units/day

- Root Cause: [material shortage | machine breakdown | labor shortage | QC issues]

Step 2 - Recovery Plan:

Option A: Overtime - +25% capacity | Cost: R50,000

Option B: Subcontract - +50% capacity | Cost: R120,000

Option C: Split Order - Air freight partial | Cost: R500,000

Step 3 - Selected Action:

- Choose Option B + Option A (combined)

- Expected Recovery: 3 days

- New Completion Date: Original + 2 days

- Net Impact on Project: 2 days delay (mitigated)

Step 4 - Communication:

- Sponsor Notification: ☑ Sent

- Stakeholder Update: ☑ Planned

- Logistics Adjustments: ☑ In Progress

- Risk Register Update: ☑ Completed

Step 5 - Monitoring:

- Daily progress checks

- QA rate monitoring

- Escalation if recovery fails

## PART 10: LOVABLE.DEV IMPLEMENTATION PROMPTS

### Prompt 1: Interactive Mindmap Setup

text

Create an interactive mindmap page as the central project dashboard. Use React Flow (or similar library) to create node-based visualization. Features required:

- 2D zoomable/panable mindmap with all main nodes (Production, Logistics, Warehousing, Distribution, Training, FirstRand, NPOs, Monitoring)

- Color coding by status (green=on_track, yellow=warning, red=delayed, blue=completed)

- Click on any node to open side panel with detailed data

- Risk overlay toggle showing risk indicators on nodes

- Real-time updates via Supabase subscriptions

- Responsive design for desktop and tablet

### Prompt 2: Node Data Integration

text

Connect mindmap nodes to real-time data from the following tables:

- inventory_batches → Production node

- deliveries → Distribution node

- training_events → Training node

- warehouses → Warehousing node

- contracts → FirstRand/NPO nodes

- kpi_tracking → Monitoring node

Show live counts and status badges on each node

### Prompt 3: Side Panel Implementation

text

Create a comprehensive side panel that opens when any mindmap node is clicked. The panel should show:

- Node summary with key metrics

- Expandable sections for detailed data

- Charts and visualizations

- Quick actions (update status, add note, escalate risk)

- Related records (deliveries, events, contracts)

- Close button and ability to click outside to close

### Prompt 4: Twilio Communication Integration

text

Integrate Twilio for all communications:

- SMS: Use Twilio SMS API for text notifications

- WhatsApp: Twilio WhatsApp Business API

- Email: Twilio SendGrid

- Push: Twilio Notify for mobile push

- Create communication templates table

- Implement automatic trigger system based on database events

- Add notification preferences per user role

### Prompt 5: Risk Management Overlay

text

Build a risk management overlay that:

- Shows colored risk indicators on all mindmap nodes

- Opens risk detail panel with severity, probability, mitigation plan

- Provides risk recovery workflows with step-by-step actions

- Tracks risk status changes over time

- Links to risk register table with full history

- Allows risk acknowledgment and closure

### Prompt 6: 3PL Integration Pipeline

text

Implement API integrations for logistics partners:

- DSV SeaFreight: Container tracking API

- DHL Global Forwarding: Air freight tracking

- M6T Logistics: Port to warehouse tracking

- Bidvest International: Sea freight status

- The Courier Guy: Last-mile delivery tracking

- Aramex: Pan-African tracking

Create unified tracking dashboard showing all shipments in real-time

## PART 11: DEPLOYMENT CHECKLIST

text

☐ 1. Copy all SQL schemas to Supabase

☐ 2. Execute RLS policies

☐ 3. Configure authentication

☐ 4. Deploy mindmap component with React Flow

☐ 5. Configure Twilio credentials

☐ 6. Set up 3PL API integrations

☐ 7. Configure Mapbox/Google Maps API

☐ 8. Set up real-time subscriptions

☐ 9. Test node interactions

☐ 10. Test communication triggers

☐ 11. Test risk overlay functionality

☐ 12. Deploy to production

## NEXT STEPS

- Copy this entire document into Lovable.dev

- Execute the SQL schemas in Supabase

- Run the prompts in sequence

- Test the mindmap with sample data

- Configure integrations (Twilio, 3PL APIs, Maps)

- Go live with the project command center