# IBX-CAREERS4AFRICA-SA26

## PROJECT DELIVERY & IMPLEMENTATION PLAN - OUTLINE

### THEME: "Launching Rockets into Careers" - Our Most Valuable Legacy, Our Learners

## PART 1: EXECUTIVE SUMMARY - The Vision

### 1.1 Project Overview

| Element | Detail |
| --- | --- |
| Project Name | IBX-CAREERS4AFRICA-SA26 |
| Theme | "Launching Rockets into Careers" |
| Tagline | Our Most Valuable Legacy, Our Learners |
| Project Owner | IBATUR Education CC |
| Sponsor | FirstRand Foundation |
| Primary PBO | CareerLinx |
| Duration | 12 Months (March 2025 - February 2026) |
| Scope | 200,000 UCG Sets (13 Volumes each) |
| Target | 20,000+ Schools, 2,991 Trainers, 1M+ Learners |

### 1.2 Brand Architecture

text

┌─────────────────────────────────────────────────────────────────────────────────────┐

│                                                                                      │

│                         🚀 IBX-CAREERS4AFRICA-SA26                                 │

│                                                                                      │

│                      "Launching Rockets into Careers"                                │

│                         Our Most Valuable Legacy, Our Learners                      │

│                                                                                      │

│  ┌─────────────────────────────────────────────────────────────────────────────────┐ │

│  │                                                                                  │ │

│  │  ┌───────────────┐  ┌───────────────┐  ┌───────────────┐  ┌───────────────┐   │ │

│  │  │  MISSION      │  │  FLEET        │  │  STAR FLEET   │  │  ROCKETS      │   │ │

│  │  │  CONTROL      │  │  COMMANDER    │  │  (Trainers)   │  │  (Learners)   │   │ │

│  │  │  (Leadership) │  │  (National)   │  │               │  │               │   │ │

│  │  └───────────────┘  └───────────────┘  └───────────────┘  └───────────────┘   │ │

│  │           │                  │                  │                  │           │ │

│  │  ┌───────────────┐  ┌───────────────┐  ┌───────────────┐  ┌───────────────┐   │ │

│  │  │  FLEET        │  │  SUPPLY       │  │  GALACTIC     │  │  OUTPOST      │   │ │

│  │  │  OUTPOSTS     │  │  FLEET        │  │  CREW         │  │  ACADEMY      │   │ │

│  │  │  (Regions)    │  │  (Logistics)  │  │  (Events)     │  │  (PBO/NPO)    │   │ │

│  │  └───────────────┘  └───────────────┘  └───────────────┘  └───────────────┘   │ │

│  │                                                                                  │ │

│  │  ┌─────────────────────────────────────────────────────────────────────────────┐ │ │

│  │  │  SPONSOR: FIRST RAND FOUNDATION + ALL OPCOs                                │ │ │

│  │  │  (FNB, WesBank, RMB, OUTsurance, Momentum, Direct Axis, Albaraka, etc.)   │ │ │

│  │  └─────────────────────────────────────────────────────────────────────────────┘ │ │

│  └─────────────────────────────────────────────────────────────────────────────────┘ │

│                                                                                      │

└─────────────────────────────────────────────────────────────────────────────────────┘

## PART 2: STAKEHOLDER HIERARCHY - "Who Is Who"

### 2.1 Space Mission Analogy Mapping

| Space Role | Project Role | Entity/Organization | Primary Responsibilities |
| --- | --- | --- | --- |
| MISSION CONTROL | Project Leadership | IBATUR Education CC | Strategic oversight, national goal-setting, resource allocation, sponsor liaison |
| FLEET COMMANDER | National Programme Manager | CareerLinx (PBO) | Manages all Fleet Outposts, monitors project KPIs, reports to Mission Control |
| FLEET OUTPOSTS | Regional Managers | CareerLinx Regional Offices | Oversees Outpost Academy, ensures training compliance, manages regional operations |
| OUTPOST ACADEMY | Training Hub | NPO/PBO Partners | Executes Star Fleet training, manages curriculum delivery |
| SUPPLY FLEET | Logistics Network | 3PL Providers + Courier Partners | Distributes career guides, manages inventory, warehouse operations |
| GALACTIC CREW | Event Team | Event Management NPOs | Organizes training events, handles venues, RSVPs, marketing activation |
| STAR FLEET | Master Trainers | Post-Grads/Matriculants/Educators | Trains Navigators, delivers guide content, conducts workshops |
| NAVIGATORS | LO Teachers | Life Orientation Educators | Teaches Rockets, implements guides, classroom delivery |
| ROCKETS | Learners | Grade 9-12 Learners | Uses career guides, provides feedback, journey to careers |
| ORBIT CONTROL | Sponsor | FirstRand Foundation | Funding, brand activation, strategic alignment |
| GROUND CONTROL | Support Services | IT, Finance, Admin | Systems support, reporting, financial management |

### 2.2 Organizational Structure Diagram

text

┌─────────────────────────────────────────────────────────────────────────────────────┐

│                                                                                      │

│                              🚀 MISSION CONTROL                                     │

│                              IBATUR Education CC                                    │

│                        (Strategic Leadership & Oversight)                           │

│                                    │                                                 │

│                          ┌─────────┴─────────┐                                      │

│                          │                   │                                      │

│                    ┌─────▼─────┐       ┌─────▼─────┐                                │

│                    │  ORBIT    │       │  GROUND   │                                │

│                    │  CONTROL  │       │  CONTROL  │                                │

│                    │  (FRF)    │       │  (Admin)  │                                │

│                    └───────────┘       └───────────┘                                │

│                          │                   │                                      │

│                          └─────────┬─────────┘                                      │

│                                    │                                                 │

│                         ┌──────────▼──────────┐                                     │

│                         │   FLEET COMMANDER   │                                     │

│                         │   CareerLinx PBO    │                                     │

│                         │  (National Manager) │                                     │

│                         └──────────┬──────────┘                                     │

│                                    │                                                 │

│         ┌──────────────────────────┼──────────────────────────┐                     │

│         │                          │                          │                     │

│    ┌────▼────┐               ┌─────▼─────┐              ┌─────▼─────┐               │

│    │ FLEET   │               │  FLEET    │              │  FLEET    │               │

│    │OUTPOST 1│               │ OUTPOST 2 │              │ OUTPOST 3 │               │

│    │Gauteng  │               │  KZN/EC   │              │ WC/NC/FS  │               │

│    └────┬────┘               └─────┬─────┘              └─────┬─────┘               │

│         │                          │                          │                     │

│    ┌────┴────┐               ┌─────┴─────┐              ┌─────┴─────┐               │

│    │OUTPOST  │               │OUTPOST     │              │OUTPOST     │               │

│    │ACADEMY  │               │ACADEMY     │              │ACADEMY     │               │

│    │(NPOs)   │               │(NPOs)      │              │(NPOs)      │               │

│    └────┬────┘               └─────┬─────┘              └─────┬─────┘               │

│         │                          │                          │                     │

│    ┌────┴────┐               ┌─────┴─────┐              ┌─────┴─────┐               │

│    │STAR     │               │STAR        │              │STAR        │               │

│    │FLEET    │               │FLEET       │              │FLEET       │               │

│    │(150     │               │(100        │              │(75         │               │

│    │Trainers)│               │Trainers)   │              │Trainers)   │               │

│    └────┬────┘               └─────┬─────┘              └─────┬─────┘               │

│         │                          │                          │                     │

│         └──────────────────────────┼──────────────────────────┘                     │

│                                    │                                                 │

│                         ┌──────────▼──────────┐                                     │

│                         │    NAVIGATORS       │                                     │

│                         │  (LO Teachers)      │                                     │

│                         │    ~10,000          │                                     │

│                         └──────────┬──────────┘                                     │

│                                    │                                                 │

│                         ┌──────────▼──────────┐                                     │

│                         │     ROCKETS          │                                     │

│                         │   (Learners)         │                                     │

│                         │  1M+ Students        │                                     │

│                         └──────────────────────┘                                     │

│                                                                                      │

└─────────────────────────────────────────────────────────────────────────────────────┘

## PART 3: PROCESS FLOWS - "What They Do When"

### 3.1 End-to-End Process Flow

text

┌─────────────────────────────────────────────────────────────────────────────────────┐

│                              PHASE 1: PRE-LAUNCH (Months 1-4)                       │

├─────────────────────────────────────────────────────────────────────────────────────┤

│                                                                                      │

│  ┌─────────────────────────────────────────────────────────────────────────────────┐ │

│  │  MISSION CONTROL                                                               │ │

│  │  • Secure funding from FirstRand Foundation                                    │ │

│  │  • Finalize project scope and budget                                           │ │

│  │  • Appoint Fleet Commander (CareerLinx)                                        │ │

│  │  • Establish Fleet Outposts (Regional offices)                                 │ │

│  │  • Select and appoint NPO/PBO partners                                         │ │

│  └─────────────────────────────────────────────────────────────────────────────────┘ │

│                                      │                                                │

│  ┌──────────────────────────────────┼────────────────────────────────────────────────┐ │

│  │  SUPPLY FLEET                    ▼                                                │ │

│  │  • Select Chinese printer partner                                               │ │

│  │  • Sign printing contract                                                       │ │

│  │  • Place order: 200,000 sets × 13 volumes                                       │ │

│  │  • Schedule production timeline                                                 │ │

│  │  • Arrange 3PL logistics partners                                               │ │

│  └─────────────────────────────────────────────────────────────────────────────────┘ │

│                                      │                                                │

│  ┌──────────────────────────────────┼────────────────────────────────────────────────┐ │

│  │  OUTPOST ACADEMY                 ▼                                                │ │

│  │  • Develop training curriculum                                                   │ │

│  │  • Recruit Star Fleet (Master Trainers)                                          │ │

│  │  • Design training materials                                                    │ │

│  │  • Plan training event schedule                                                 │ │

│  └─────────────────────────────────────────────────────────────────────────────────┘ │

│                                                                                      │

└─────────────────────────────────────────────────────────────────────────────────────┘

│

▼

┌─────────────────────────────────────────────────────────────────────────────────────┐

│                              PHASE 2: PRODUCTION (Months 4-7)                       │

├─────────────────────────────────────────────────────────────────────────────────────┤

│                                                                                      │

│  ┌─────────────────────────────────────────────────────────────────────────────────┐ │

│  │  SUPPLY FLEET - CHINA PRODUCTION                                                │ │

│  │  • Pre-press approval (content sign-off)                                       │ │

│  │  • Sample printing (ISO compliance check)                                      │ │

│  │  • Bulk production (200,000 sets)                                              │ │

│  │  • Quality inspection (in-process + pre-shipment)                              │ │

│  │  • Packing: 2 sets/carton → 100,000 cartons                                    │ │

│  │  • Palletizing → 1,667 pallets                                                 │ │

│  │  • Container loading → 55 × 40ft containers                                    │ │

│  │  • Export customs clearance                                                    │ │

│  │  • Video/photographic documentation of process                                 │ │

│  └─────────────────────────────────────────────────────────────────────────────────┘ │

│                                      │                                                │

│  ┌──────────────────────────────────┼────────────────────────────────────────────────┐ │

│  │  AIR FREIGHT TRAINER CONSIGNMENT  ▼ (10,000 Sets)                                │ │

│  │  • Priority air freight (5-7 days transit)                                      │ │

│  │  • Arrive at OR Tambo, Johannesburg                                             │ │

│  │  • Express customs clearance                                                    │ │

│  │  • Immediate delivery to training venues                                        │ │

│  └─────────────────────────────────────────────────────────────────────────────────┘ │

│                                      │                                                │

│  ┌──────────────────────────────────┼────────────────────────────────────────────────┐ │

│  │  SEA FREIGHT BULK                 ▼ (190,000 Sets)                               │ │

│  │  • Depart China ports (Shanghai/Shenzhen/Guangzhou)                             │ │

│  │  • 28-35 days sea transit                                                       │ │

│  │  • Daily GPS vessel tracking (every 3 hours)                                    │ │

│  │  • Arrive Durban Port (primary) + Cape Town                                     │ │

│  │  • SARS customs clearance process                                               │ │

│  │  • Release to 3PL warehouse network                                             │ │

│  └─────────────────────────────────────────────────────────────────────────────────┘ │

│                                                                                      │

└─────────────────────────────────────────────────────────────────────────────────────┘

│

▼

┌─────────────────────────────────────────────────────────────────────────────────────┐

│                          PHASE 3: WAREHOUSING (Months 7-9)                          │

├─────────────────────────────────────────────────────────────────────────────────────┤

│                                                                                      │

│  ┌─────────────────────────────────────────────────────────────────────────────────┐ │

│  │  SUPPLY FLEET - WAREHOUSE NETWORK                                               │ │

│  │                                                                                  │ │

│  │  ┌─────────────────────────────────────────────────────────────────────────────┐ │ │

│  │  │  TIER 1: PRIMARY WAREHOUSE                                                   │ │ │

│  │  │  Johannesburg (1,500 sqm, 500,000 guides capacity)                          │ │ │

│  │  │  • Receiving, QC, break-bulk, re-palletizing by province                   │ │ │

│  │  └─────────────────────────────────────────────────────────────────────────────┘ │ │

│  │                          │                                                       │ │

│  │            ┌─────────────┼─────────────────────────────────────┐                │ │

│  │            │             │                                     │                │ │

│  │  ┌─────────▼─────────┐ ┌─▼──────────────────┐ ┌───────────────▼──────────────┐ │ │

│  │  │ TIER 2: REGIONAL  │ │ TIER 2: REGIONAL   │ │ TIER 2: REGIONAL             │ │ │

│  │  │ Cape Town         │ │ Durban             │ │ Gqeberha (PE)                │ │ │

│  │  │ 1,000 sqm         │ │ 800 sqm            │ │ 600 sqm                      │ │ │

│  │  └─────────┬─────────┘ └─┬──────────────────┘ └───────────────┬──────────────┘ │ │

│  │            │             │                                     │                │ │

│  │            └─────────────┼─────────────────────────────────────┘                │ │

│  │                          │                                                       │ │

│  │            ┌─────────────┼─────────────────────────────────────┐                │ │

│  │            │             │                                     │                │ │

│  │  ┌─────────▼─────────┐ ┌─▼──────────────────┐ ┌───────────────▼──────────────┐ │ │

│  │  │ TIER 3: SATELLITE │ │ TIER 3: SATELLITE  │ │ TIER 3: SATELLITE           │ │ │

│  │  │ Polokwane         │ │ Bloemfontein       │ │ Kimberley                   │ │ │

│  │  │ Rustenburg        │ │ Upington           │ │ Mbombela                    │ │ │

│  │  │ Mahikeng          │ │ Vredendal          │ │ Pietermaritzburg            │ │ │

│  │  │ Potchefstroom     │ │ East London        │ │                             │ │ │

│  │  └───────────────────┘ └────────────────────┘ └─────────────────────────────┘ │ │

│  │                                                                                  │ │

│  └─────────────────────────────────────────────────────────────────────────────────┘ │

│                                                                                      │

└─────────────────────────────────────────────────────────────────────────────────────┘

│

▼

┌─────────────────────────────────────────────────────────────────────────────────────┐

│                        PHASE 4: DISTRIBUTION (Months 8-11)                          │

├─────────────────────────────────────────────────────────────────────────────────────┤

│                                                                                      │

│  ┌─────────────────────────────────────────────────────────────────────────────────┐ │

│  │  SUPPLY FLEET - LAST MILE DELIVERY                                              │ │

│  │                                                                                  │ │

│  │  ┌─────────────────────────────────────────────────────────────────────────────┐ │ │

│  │  │  COURIER PARTNERS (National + Regional)                                    │ │ │

│  │  │  • The Courier Guy: Urban/Peri-urban (24-48 hours)                         │ │ │

│  │  │  • Aramex: Pan-African + Rural (48-72 hours)                               │ │ │

│  │  │  • DHL Express: Premium/Urgent (24 hours)                                  │ │ │

│  │  │  • FedEx: Express services                                                  │ │ │

│  │  │  • Local couriers: Remote areas (3-5 days)                                 │ │ │

│  │  └─────────────────────────────────────────────────────────────────────────────┘ │ │

│  │                                                                                  │ │

│  │  ┌─────────────────────────────────────────────────────────────────────────────┐ │ │

│  │  │  DELIVERY ACKNOWLEDGEMENT SYSTEM                                            │ │ │

│  │  │  • GPS location capture                                                     │ │ │

│  │  │  • Digital signature (recipient)                                            │ │ │

│  │  │  • ID verification (last 4 digits)                                          │ │ │

│  │  │  • Photo proof of delivery                                                  │ │ │

│  │  │  • Real-time status updates                                                 │ │ │

│  │  │  • Real-time push notifications                                             │ │ │

│  │  └─────────────────────────────────────────────────────────────────────────────┘ │ │

│  └─────────────────────────────────────────────────────────────────────────────────┘ │

│                                      │                                                │

│  ┌──────────────────────────────────┼────────────────────────────────────────────────┐ │

│  │  GALACTIC CREW                   ▼                                                │ │

│  │  • Coordinate training events with DBE                                          │ │

│  │  • Book venues (Thusong Centres, Civic Centres, DBE Offices)                    │ │

│  │  • Invite LO teachers                                                           │ │

│  │  • Manage RSVPs and attendance                                                 │ │

│  │  • Set up marketing stands (FirstRand OPCOs)                                   │ │

│  │  • Photography/videography coverage                                            │ │

│  │  • Social media content creation                                                │ │

│  └─────────────────────────────────────────────────────────────────────────────────┘ │

│                                                                                      │

└─────────────────────────────────────────────────────────────────────────────────────┘

│

▼

┌─────────────────────────────────────────────────────────────────────────────────────┐

│                        PHASE 5: TRAINING (Months 9-12)                               │

├─────────────────────────────────────────────────────────────────────────────────────┤

│                                                                                      │

│  ┌─────────────────────────────────────────────────────────────────────────────────┐ │

│  │  OUTPOST ACADEMY + STAR FLEET + NAVIGATORS                                     │ │

│  │                                                                                  │ │

│  │  ┌─────────────────────────────────────────────────────────────────────────────┐ │ │

│  │  │  TRAINER OF TRAINERS (Master Trainers)                                      │ │ │

│  │  │  • 17 Lead Trainers + 34 Assistant Trainers                                 │ │ │

│  │  │  • Trained by OUTPOST ACADEMY                                               │ │ │

│  │  └─────────────────────────────────────────────────────────────────────────────┘ │ │

│  │                                      │                                            │ │

│  │  ┌───────────────────────────────────┼────────────────────────────────────────────┐ │

│  │  │  STAR FLEET - 2,991 Trainers     ▼                                            │ │

│  │  │  • Post-grads, Matriculants, Experienced Educators                           │ │

│  │  │  • Trained across 9 provinces                                               │ │

│  │  │  • Training events at 200+ venues                                           │ │

│  │  └─────────────────────────────────────────────────────────────────────────────┘ │ │

│  │                                      │                                            │ │

│  │  ┌───────────────────────────────────┼────────────────────────────────────────────┐ │

│  │  │  NAVIGATORS - 10,000+ LO Teachers  ▼                                          │ │

│  │  │  • Receive UCG sets at training events                                      │ │

│  │  │  • Attend training workshops                                               │ │

│  │  │  • Learn guide implementation                                              │ │

│  │  └─────────────────────────────────────────────────────────────────────────────┘ │ │

│  │                                      │                                            │ │

│  │  ┌───────────────────────────────────┼────────────────────────────────────────────┐ │

│  │  │  ROCKETS - 1M+ Learners            ▼                                          │ │

│  │  │  • Receive UCG guides in classrooms                                         │ │

│  │  │  • Complete career exploration activities                                   │ │

│  │  │  • Provide feedback through surveys                                        │ │

│  │  └─────────────────────────────────────────────────────────────────────────────┘ │ │

│  └─────────────────────────────────────────────────────────────────────────────────┘ │

│                                                                                      │

└─────────────────────────────────────────────────────────────────────────────────────┘

│

▼

┌─────────────────────────────────────────────────────────────────────────────────────┐

│                        PHASE 6: MONITORING & IMPACT (Months 10-12+)                 │

├─────────────────────────────────────────────────────────────────────────────────────┤

│                                                                                      │

│  ┌─────────────────────────────────────────────────────────────────────────────────┐ │

│  │  GROUND CONTROL - MONITORING & EVALUATION                                       │ │

│  │                                                                                  │ │

│  │  ┌─────────────────────────────────────────────────────────────────────────────┐ │ │

│  │  │  KPI TRACKING                                                               │ │ │

│  │  │  • Order Fulfillment Rate: Target >98%                                      │ │ │

│  │  │  • On-Time Delivery Rate: Target >95%                                       │ │ │

│  │  │  • Order Accuracy: Target >99%                                              │ │ │

│  │  │  • Teacher Training Attendance: Target >90%                                 │ │ │

│  │  │  • Implementation Rate: Target >85%                                         │ │ │

│  │  └─────────────────────────────────────────────────────────────────────────────┘ │ │

│  │                                                                                  │ │

│  │  ┌─────────────────────────────────────────────────────────────────────────────┐ │ │

│  │  │  NPO REPORTING                                                              │ │ │

│  │  │  • Monthly reports from all NPOs                                            │ │ │

│  │  │  • KPI achievement tracking                                                │ │ │

│  │  │  • Event attendance analysis                                                │ │ │

│  │  │  • Delivery confirmation verification                                      │ │ │

│  │  └─────────────────────────────────────────────────────────────────────────────┘ │ │

│  │                                                                                  │ │

│  │  ┌─────────────────────────────────────────────────────────────────────────────┐ │ │

│  │  │  FIRST RAND FOUNDATION REPORTING                                            │ │ │

│  │  │  • Weekly progress updates                                                  │ │ │

│  │  │  • Monthly performance dashboards                                           │ │ │

│  │  │  • Quarterly impact reports                                                 │ │ │

│  │  │  • Final project evaluation report                                          │ │ │

│  │  │  • Media & social impact analysis                                           │ │ │

│  │  └─────────────────────────────────────────────────────────────────────────────┘ │ │

│  └─────────────────────────────────────────────────────────────────────────────────┘ │

│                                                                                      │

└─────────────────────────────────────────────────────────────────────────────────────┘

## PART 4: SPACE THEME STAKEHOLDER MATRIX

### 4.1 Complete Role Matrix

| Space Role | Project Role | Responsible Entity | Count | Key Deliverables |
| --- | --- | --- | --- | --- |
| MISSION CONTROL | Executive Leadership | IBATUR Education CC | 1 | Strategic decisions, budget approval, sponsor relationship |
| ORBIT CONTROL | Sponsor | FirstRand Foundation | 1 | Funding, brand integration, strategic alignment |
| FLEET COMMANDER | National Programme Manager | CareerLinx (PBO) | 1 | Overall project coordination, KPI monitoring, reporting |
| FLEET OUTPOSTS | Regional Managers | CareerLinx Regional | 9 | Regional coordination, training oversight, compliance |
| OUTPOST ACADEMY | Training Hub Management | NPO Partners | 9+ | Trainer training, curriculum delivery, quality assurance |
| SUPPLY FLEET | Logistics & 3PL | 3PL Providers | 8+ | Warehousing, distribution, inventory management |
| GALACTIC CREW | Event Management | Event NPOs | 9+ | Event coordination, venue management, marketing |
| STAR FLEET | Master Trainers | Post-Grads/Educators | 2,991 | Training delivery, guide content, workshops |
| NAVIGATORS | LO Teachers | School Educators | 10,000+ | Guide implementation, classroom delivery |
| ROCKETS | Learners | Students | 1M+ | Feedback, engagement, career exploration |
| GROUND CONTROL | Support Services | Admin/IT/Finance | 15+ | Systems, reporting, financials |

## PART 5: KEY PARTNER LIST

### 5.1 3PL Logistics Partners

| Partner | Role | Service | API Integration |
| --- | --- | --- | --- |
| DSV SeaFreight | Sea Freight Forwarder | Container management, customs brokerage | Yes |
| DHL Global Forwarding | Air Freight | Trainer consignment (10,000 sets) | Yes |
| M6T Logistics | Port to Warehouse | Container tracking, distribution | Yes |
| Bidvest International | Sea Freight | Bulk shipment consolidation | Yes |
| Rhenus Logistics | Multi-modal | Project cargo, customs clearance | Yes |
| Stoble Logistics | Last-Mile | Regional distribution | Yes |
| Transitex Logistics | Port Logistics | Customs clearance, warehousing | Yes |
| Value Logistics | Supply Chain | Distribution, tracking | Yes |
| The Courier Guy | Last-Mile Delivery | Urban/peri-urban delivery | Yes |
| Aramex | Pan-African Delivery | Rural + regional delivery | Yes |
| DHL Express | Express Delivery | Premium/urgent delivery | Yes |
| FedEx | Express Delivery | Express services | Yes |

### 5.2 NPO/PBO Partners

| Partner | Region | Trainers | Schools | Contract Value |
| --- | --- | --- | --- | --- |
| CareerLinx (Primary) | National | 150 | 2,500 | R12,000,000 |
| EduNPO SA | Gauteng, WC | 45 | 800 | R4,500,000 |
| TeachSA Foundation | KZN, EC | 38 | 700 | R3,800,000 |
| CareerAccess NPO | FS, NC | 25 | 500 | R2,900,000 |
| EdUnity Project | Limpopo, Mpumalanga | 18 | 400 | R2,100,000 |
| SchoolConnect SA | NW, Mpumalanga | 15 | 350 | R1,800,000 |
| EduRise NPO | Rural Clusters | 10 | 200 | R1,200,000 |
| YouthImpact PBO | Township Clusters | 8 | 150 | R950,000 |
| CommunityEd Network | Remote Areas | 6 | 120 | R750,000 |

## PART 6: FRF BUY-IN CASE - "Why This Matters"

### 6.1 Strategic Alignment with FRF Objectives

text

┌─────────────────────────────────────────────────────────────────────────────────────┐

│                    FIRST RAND FOUNDATION STRATEGIC ALIGNMENT                        │

├─────────────────────────────────────────────────────────────────────────────────────┤

│                                                                                      │

│  ┌─────────────────────────────────────────────────────────────────────────────────┐ │

│  │  FRF STRATEGIC PILLAR                        │  PROJECT CONTRIBUTION            │ │

│  │  ─────────────────────────────────────────────┼───────────────────────────────────┤ │

│  │  Education & Youth Development                │ Career guidance for 1M+ learners  │ │

│  │  Enterprise & Supplier Development            │ NPO capacity building             │ │

│  │  Job Creation & Skills Development            │ 2,991 trainers employed           │ │

│  │  Community Investment                         │ 20,000+ schools reached           │ │

│  │  Brand Building & Social Impact              │ Brand visibility across SA        │ │

│  └─────────────────────────────────────────────────────────────────────────────────┘ │

│                                                                                      │

│  ┌─────────────────────────────────────────────────────────────────────────────────┐ │

│  │  FRF OPCO BRAND ACTIVATION                                                      │ │

│  │  ┌─────────────────────────────────────────────────────────────────────────────┐ │ │

│  │  │  OPCO                  │  EVENT PRESENCE         │  BRAND TOUCHPOINTS       │ │ │

│  │  ├────────────────────────┼─────────────────────────┼──────────────────────────┤ │ │

│  │  │  FNB                   │  Youth Banking Stands   │  Career finance literacy │ │ │

│  │  │  WesBank               │  Career & Mobility      │  Vehicle finance for     │ │ │

│  │  │                        │                         │  aspiring graduates      │ │ │

│  │  │  RMB                   │  Investment Careers     │  Financial sector        │ │ │

│  │  │                        │                         │  career pathways         │ │ │

│  │  │  OUTsurance            │  Insurance Awareness    │  Risk & insurance        │ │ │

│  │  │  Momentum Metropolitan │  Wellness & Financial   │  Health & wealth         │ │ │

│  │  │  Direct Axis           │  Consumer Finance       │  Accessible lending      │ │ │

│  │  │  Albaraka Bank         │  Islamic Banking       │  Inclusive finance       │ │ │

│  │  └─────────────────────────────────────────────────────────────────────────────┘ │ │

│  └─────────────────────────────────────────────────────────────────────────────────┘ │

│                                                                                      │

└─────────────────────────────────────────────────────────────────────────────────────┘

### 6.2 Social Impact Metrics for FRF Reporting

| Metric | Target | Measurement Method | Reporting Frequency |
| --- | --- | --- | --- |
| Learners Reached | 1,000,000+ | School attendance records | Monthly |
| Schools Reached | 20,000+ | Delivery confirmation | Monthly |
| Teachers Trained | 10,000+ | Event attendance records | Per event |
| Star Fleet Trained | 2,991 | Training certificates | Monthly |
| NPOs Empowered | 9+ | Contract KPIs | Monthly |
| Jobs Created | 2,991+ | Trainer employment records | Monthly |
| Social Media Reach | 5M+ | Platform analytics | Weekly |
| Brand Impressions | 20M+ | Advertising metrics | Monthly |
| Career Guidance Impact | 85%+ | Learner surveys | Quarterly |
| Community Engagement | 90%+ | Event attendance | Per event |

## PART 7: NEXT STEPS

### 7.1 Immediate Actions Required

| # | Action Item | Responsible | Timeline |
| --- | --- | --- | --- |
| 1 | Finalize FRF sponsorship agreement | IBATUR/FRF | Week 1 |
| 2 | Sign primary PBO contract (CareerLinx) | IBATUR/CareerLinx | Week 2 |
| 3 | Appoint Fleet Outpost Managers | CareerLinx | Week 2-3 |
| 4 | Select NPO partners per region | Fleet Commander | Week 3-4 |
| 5 | Finalize Chinese printer selection | IBATUR Procurement | Week 2 |
| 6 | Sign printing contract (200,000 sets) | IBATUR/Printer | Week 4 |
| 7 | Select 3PL partners | IBATUR Logistics | Week 3-4 |
| 8 | Place trainer consignment order (10,000 sets) | IBATUR/Printer | Week 5 |
| 9 | Begin Zoho implementation | IT Team | Week 1 |
| 10 | Launch Lovable.dev web app | IT Team | Week 2 |

## READY FOR YOUR INSTRUCTIONS

I have outlined the complete project structure including:

- ✅ Brand Theme - "Launching Rockets into Careers" with full space analogy

- ✅ Stakeholder Hierarchy - Who is who (Mission Control → Rockets)

- ✅ Process Flows - What they do when (6 Phases from Pre-Launch to Impact)

- ✅ Role Matrix - Complete stakeholder mapping

- ✅ Partner Lists - 3PL + NPO partners

- ✅ FRF Buy-In Case - Why this matters to FirstRand Foundation

- ✅ Implementation Timeline - 12-month rollout