# IBX-CAREERS4AFRICA-SA26

## COMPREHENSIVE PROJECT PLANNING TOOL

### Integrated Gantt Charts, Timelines, Sub-items, and 3PL Logistics Management

## EXECUTIVE OVERVIEW

This document outlines a comprehensive project planning tool designed specifically for the IBX-CAREERS4AFRICA-SA26 project. The tool integrates:

- Full value-chain 3PL network modeling from manufacturing to Direct-to-School delivery

- End-to-end fulfillment orchestration with real-time tracking

- Risk management and escalation workflows with automated communication

- Dynamic dashboard integration for monitoring and evaluation

- Cost and budget management with event-level granularity

- Two-way data propagation between planning and execution systems

## PART 1: PROJECT PLANNING TOOL ARCHITECTURE

### 1.1 System Overview

text

┌─────────────────────────────────────────────────────────────────────────────────────┐

│                                                                                      │

│  ┌─────────────────────────────────────────────────────────────────────────────────┐ │

│  │  🚀 IBX-CAREERS4AFRICA-SA26 PROJECT PLANNING TOOL                              │ │

│  │                                                                                  │ │

│  │  ┌─────────────────┐  ┌─────────────────┐  ┌─────────────────┐                  │ │

│  │  │  STRATEGIC       │  │  OPERATIONAL    │  │  EXECUTION      │                  │ │

│  │  │  LAYER           │  │  LAYER          │  │  LAYER          │                  │ │

│  │  │                  │  │                  │  │                  │                  │ │

│  │  │  • Network       │  │  • Order        │  │  • Warehouse     │                  │ │

│  │  │    Design        │  │    Management   │  │    Operations    │                  │ │

│  │  │  • Greenfield    │  │  • Inventory    │  │  • Pick/Pack/    │                  │ │

│  │  │    Analysis      │  │    Optimization │  │    Ship          │                  │ │

│  │  │  • Facility      │  │  • Transportation│  │  • Last-Mile    │                  │ │

│  │  │    Location      │  │    Planning     │  │    Delivery      │                  │ │

│  │  │  • Cost-to-Serve │  │  • Route        │  │  • Returns       │                  │ │

│  │  │    Modeling      │  │    Optimization │  │    Management    │                  │ │

│  │  └─────────────────┘  └─────────────────┘  └─────────────────┘                  │ │

│  │           │                    │                    │                           │ │

│  │           └────────────────────┼────────────────────┘                           │ │

│  │                                ▼                                                │ │

│  │  ┌─────────────────────────────────────────────────────────────────────────────┐ │ │

│  │  │  INTEGRATION LAYER                                                          │ │ │

│  │  │  • Supabase Database (PostgreSQL)                                          │ │ │

│  │  │  • Zoho Suite (CRM, Inventory, Books, Creator, Flow, Analytics)            │ │ │

│  │  │  • 3PL API Gateway (DSV, DHL, M6T, Bidvest, Rhenus, Stoble, Transitex)    │ │ │

│  │  │  • Courier APIs (Courier Guy, Aramex, DHL Express, FedEx)                  │ │ │

│  │  │  • Twilio (SMS, WhatsApp, Email, Push)                                    │ │ │

│  │  └─────────────────────────────────────────────────────────────────────────────┘ │ │

│  │                                                                                  │ │

│  └─────────────────────────────────────────────────────────────────────────────────┘ │

│                                                                                      │

└─────────────────────────────────────────────────────────────────────────────────────┘

### 1.2 Software Stack Integration

| Layer | Tool/Platform | Purpose | Integration Method |
| --- | --- | --- | --- |
| Strategic Design | Optilogic Cosmic Frog | Facility location, risk scoring, scenario testing | API → Supabase |
| Network Modeling | AIMMS SC Navigator | Cost-to-serve, warehouse optimization, greenfield analysis | Data Export → Zoho |
| Simulation | AnyLogistix | Dynamic simulation, safety stock calculation | Batch Import |
| End-to-End Planning | SAP IBP | Demand planning, supply synchronization, order-based planning | REST API → Zoho |
| Fulfillment Platform | Stord | DTC fulfillment, order management, multi-node inventory | API → Zoho Inventory |
| Transportation Mgmt | Descartes | Multi-modal TMS, global visibility, cost analytics | Webhook → Supabase |
| Warehouse Mgmt | Extensiv 3PL WMS | Pick/pack/ship, inventory tracking, billing | API → Zoho Inventory |
| Web App Frontend | Lovable.dev | Sponsor portal, dashboards, mindmap, project planning | Supabase Real-time |
| Project Scheduling | Custom pjplan-based | Gantt charts, critical path, resource allocation | Python → Supabase |

## PART 2: GANTT CHART & TIMELINE STRUCTURE

### 2.1 Master Project Timeline (12 Months)

text

┌─────────────────────────────────────────────────────────────────────────────────────────────────────────────────────┐

│  IBX-CAREERS4AFRICA-SA26 - MASTER PROJECT TIMELINE                                                                  │

├─────────────────────────────────────────────────────────────────────────────────────────────────────────────────────┤

│                                                                                                                      │

│  PHASE 1: PRE-LAUNCH (Months 1-4)                                                                                   │

│  ┌─────────────────────────────────────────────────────────────────────────────────────────────────────────────────┐ │

│  │ M1 │ M2 │ M3 │ M4 │                                                                                             │ │

│  ├────┼────┼────┼────┤                                                                                             │ │

│  │ ███████████████████████████████████████████████████████████████████████████████ │                               │ │

│  │ 1.1 Sponsor Agreement & Funding (FRF)                                                                          │ │

│  │ ███████████████████████████████████████████████████████████████████████████████ │                               │ │

│  │ 1.2 PBO Contract (CareerLinx)                                                                                  │ │

│  │ ███████████████████████████████████████████████████████████████████████████████ │                               │ │

│  │ 1.3 Network Design & Greenfield Analysis (Optilogic)                                                           │ │

│  │ ███████████████████████████████████████████████████████████████████████████████ │                               │ │

│  │ 1.4 Printer Selection & Contract (China)                                                                       │ │

│  │ ███████████████████████████████████████████████████████████████████████████████ │                               │ │

│  │ 1.5 3PL Partner Selection & Contracts                                                                          │ │

│  │ ███████████████████████████████████████████████████████████████████████████████ │                               │ │

│  │ 1.6 NPO Partner Selection & Training                                                                           │ │

│  │ ███████████████████████████████████████████████████████████████████████████████ │                               │ │

│  │ 1.7 System Integration (Zoho, Lovable, Twilio)                                                                 │ │

│  └─────────────────────────────────────────────────────────────────────────────────────────────────────────────────┘ │

│                                                                                                                      │

│  PHASE 2: PRODUCTION (Months 4-7)                                                                                   │

│  ┌─────────────────────────────────────────────────────────────────────────────────────────────────────────────────┐ │

│  │ M4 │ M5 │ M6 │ M7 │                                                                                             │ │

│  ├────┼────┼────┼────┤                                                                                             │ │

│  │ ███████████████████████████████████████████████████████████████████████████████ │                               │ │

│  │ 2.1 Pre-press & Content Sign-off                                                                               │ │

│  │ ███████████████████████████████████████████████████████████████████████████████ │                               │ │

│  │ 2.2 Sample Printing & ISO Compliance                                                                           │ │

│  │ ███████████████████████████████████████████████████████████████████████████████ │                               │ │

│  │ 2.3 Bulk Production (200,000 sets)                                                                             │ │

│  │ ███████████████████████████████████████████████████████████████████████████████ │                               │ │

│  │ 2.4 Quality Inspection (In-process + Pre-shipment)                                                             │ │

│  │ ███████████████████████████████████████████████████████████████████████████████ │                               │ │

│  │ 2.5 Packing & Container Loading (55 × 40ft)                                                                    │ │

│  └─────────────────────────────────────────────────────────────────────────────────────────────────────────────────┘ │

│                                                                                                                      │

│  PHASE 3: LOGISTICS & SHIPPING (Months 6-9)                                                                         │

│  ┌─────────────────────────────────────────────────────────────────────────────────────────────────────────────────┐ │

│  │ M6 │ M7 │ M8 │ M9 │                                                                                             │ │

│  ├────┼────┼────┼────┤                                                                                             │ │

│  │ ███████████████████████████████████████████████████████████████████████████████ │                               │ │

│  │ 3.1 Air Freight (Trainer Consignment 10,000 sets - DHL Global)                                                  │ │

│  │ ███████████████████████████████████████████████████████████████████████████████ │                               │ │

│  │ 3.2 Sea Freight - Vessel Loading & Departure (DSV/Bidvest/Rhenus)                                               │ │

│  │ ███████████████████████████████████████████████████████████████████████████████ │                               │ │

│  │ 3.3 Daily Vessel GPS Tracking (Every 3 hours)                                                                   │ │

│  │ ███████████████████████████████████████████████████████████████████████████████ │                               │ │

│  │ 3.4 Port Arrival & Customs Clearance (Durban/Cape Town)                                                         │ │

│  │ ███████████████████████████████████████████████████████████████████████████████ │                               │ │

│  │ 3.5 3PL Warehouse Network Receipt (All 15+ Locations)                                                           │ │

│  └─────────────────────────────────────────────────────────────────────────────────────────────────────────────────┘ │

│                                                                                                                      │

│  PHASE 4: DISTRIBUTION (Months 8-11)                                                                                │

│  ┌─────────────────────────────────────────────────────────────────────────────────────────────────────────────────┐ │

│  │ M8 │ M9 │ M10│ M11│                                                                                             │ │

│  ├────┼────┼────┼────┤                                                                                             │ │

│  │ ███████████████████████████████████████████████████████████████████████████████ │                               │ │

│  │ 4.1 Last-Mile Delivery - Urban (Courier Guy/DHL Express)                                                         │ │

│  │ ███████████████████████████████████████████████████████████████████████████████ │                               │ │

│  │ 4.2 Last-Mile Delivery - Peri-urban (Aramex/FedEx)                                                              │ │

│  │ ███████████████████████████████████████████████████████████████████████████████ │                               │ │

│  │ 4.3 Last-Mile Delivery - Rural/Remote (Local Couriers)                                                          │ │

│  │ ███████████████████████████████████████████████████████████████████████████████ │                               │ │

│  │ 4.4 Delivery Confirmation & Digital POD (GPS, Signature, Photo)                                                 │ │

│  └─────────────────────────────────────────────────────────────────────────────────────────────────────────────────┘ │

│                                                                                                                      │

│  PHASE 5: TRAINING & EVENTS (Months 9-12)                                                                           │

│  ┌─────────────────────────────────────────────────────────────────────────────────────────────────────────────────┐ │

│  │ M9 │ M10│ M11│ M12│                                                                                             │ │

│  ├────┼────┼────┼────┤                                                                                             │ │

│  │ ███████████████████████████████████████████████████████████████████████████████ │                               │ │

│  │ 5.1 Trainer of Trainers Program (17 Lead + 34 Assistant)                                                        │ │

│  │ ███████████████████████████████████████████████████████████████████████████████ │                               │ │

│  │ 5.2 Star Fleet Training (2,991 Trainers across 9 Provinces)                                                     │ │

│  │ ███████████████████████████████████████████████████████████████████████████████ │                               │ │

│  │ 5.3 LO Teacher Workshops (10,000+ Teachers)                                                                     │ │

│  │ ███████████████████████████████████████████████████████████████████████████████ │                               │ │

│  │ 5.4 FirstRand OPCO Marketing Activation (All Events)                                                            │ │

│  └─────────────────────────────────────────────────────────────────────────────────────────────────────────────────┘ │

│                                                                                                                      │

│  PHASE 6: MONITORING & IMPACT (Months 10-12+)                                                                       │

│  ┌─────────────────────────────────────────────────────────────────────────────────────────────────────────────────┐ │

│  │ M10│ M11│ M12│ M13+                                                                                             │ │

│  ├────┼────┼────┼─────┤                                                                                             │ │

│  │ ███████████████████████████████████████████████████████████████████████████████ │                               │ │

│  │ 6.1 KPI Tracking & Monthly Reporting (NPOs)                                                                      │ │

│  │ ███████████████████████████████████████████████████████████████████████████████ │                               │ │

│  │ 6.2 FRF Impact Reports (Weekly/Monthly/Quarterly)                                                               │ │

│  │ ███████████████████████████████████████████████████████████████████████████████ │                               │ │

│  │ 6.3 Risk Management & Escalation Resolution                                                                     │ │

│  │ ███████████████████████████████████████████████████████████████████████████████ │                               │ │

│  │ 6.4 Final Project Evaluation & Sustainability Plan                                                              │ │

│  └─────────────────────────────────────────────────────────────────────────────────────────────────────────────────┘ │

│                                                                                                                      │

└─────────────────────────────────────────────────────────────────────────────────────────────────────────────────────┘

### 2.2 Detail Level: 3PL Logistics Sub-items

text

┌─────────────────────────────────────────────────────────────────────────────────────────────────────────────────────┐

│  3PL LOGISTICS - DETAILED SUB-ITEMS                                                                                 │

├─────────────────────────────────────────────────────────────────────────────────────────────────────────────────────┤

│                                                                                                                      │

│  ┌─────────────────────────────────────────────────────────────────────────────────────────────────────────────────┐ │

│  │  CHINA PRODUCTION (200,000 Sets × 13 Volumes)                                                                   │ │

│  ├─────────────────────────────────────────────────────────────────────────────────────────────────────────────────┤ │

│  │  Sub-item 1.1: Pre-press Approval (Content + ISO Compliance)                   | Days 1-14 | 🔴 Critical        │ │

│  │  Sub-item 1.2: Sample Printing (500 sets for approval)                         | Days 8-21 | 🟡 High            │ │

│  │  Sub-item 1.3: Bulk Production Start                                           | Day 22    | 🔴 Critical        │ │

│  │  Sub-item 1.4: Production Milestone 1 (25% - 50,000 sets)                      | Day 45    | 🟡 High            │ │

│  │  Sub-item 1.5: In-process QC Inspection 1                                      | Day 46    | 🟡 High            │ │

│  │  Sub-item 1.6: Production Milestone 2 (50% - 100,000 sets)                     | Day 60    | 🟡 High            │ │

│  │  Sub-item 1.7: In-process QC Inspection 2                                      | Day 61    | 🟡 High            │ │

│  │  Sub-item 1.8: Production Milestone 3 (75% - 150,000 sets)                     | Day 75    | 🟡 High            │ │

│  │  Sub-item 1.9: Production Completion (200,000 sets)                            | Day 90    | 🔴 Critical        │ │

│  │  Sub-item 1.10: Final QC Inspection (1% sample = 2,000 sets)                   | Days 91-93| 🟡 High            │ │

│  │  Sub-item 1.11: QC Pass/Fail Report Generation                                 | Day 94    | 🟡 High            │ │

│  │  Sub-item 1.12: Packing (2 sets/carton → 100,000 cartons)                      | Days 95-100| 🟡 High            │ │

│  │  Sub-item 1.13: Palletizing (1,667 pallets)                                    | Days 101-105| 🟢 Medium          │ │

│  │  Sub-item 1.14: Container Loading (55 × 40ft containers)                       | Days 106-110| 🟡 High            │ │

│  │  Sub-item 1.15: Container Sealing & GPS Tagging                                | Day 111   | 🟢 Medium          │ │

│  │  Sub-item 1.16: Export Customs Clearance (China)                               | Days 112-115| 🔴 Critical        │ │

│  └─────────────────────────────────────────────────────────────────────────────────────────────────────────────────┘ │

│                                                                                                                      │

│  ┌─────────────────────────────────────────────────────────────────────────────────────────────────────────────────┐ │

│  │  AIR FREIGHT - TRAINER CONSIGNMENT (10,000 Sets)                                                                │ │

│  ├─────────────────────────────────────────────────────────────────────────────────────────────────────────────────┤ │

│  │  Sub-item 2.1: Air Waybill Generation (DHL Global Forwarding)                  | Day 95    | 🟡 High            │ │

│  │  Sub-item 2.2: Trucking to China Airport                                       | Day 96    | 🟢 Medium          │ │

│  │  Sub-item 2.3: Air Freight Departure                                           | Day 97    | 🔴 Critical        │ │

│  │  Sub-item 2.4: Daily Air Tracking Update (Every 3 hours)                       | Days 98-102| 🟢 Medium          │ │

│  │  Sub-item 2.5: Arrival at OR Tambo (Johannesburg)                              | Day 102   | 🔴 Critical        │ │

│  │  Sub-item 2.6: Express Customs Clearance                                       | Day 102   | 🔴 Critical        │ │

│  │  Sub-item 2.7: Tender to 3PL for Training Venue Delivery                       | Day 102   | 🟡 High            │ │

│  │  Sub-item 2.8: Delivery to Training Events (All 9 Provinces)                   | Days 103-110| 🟡 High            │ │

│  └─────────────────────────────────────────────────────────────────────────────────────────────────────────────────┘ │

│                                                                                                                      │

│  ┌─────────────────────────────────────────────────────────────────────────────────────────────────────────────────┐ │

│  │  SEA FREIGHT - BULK CONSIGNMENT (190,000 Sets)                                                                  │ │

│  ├─────────────────────────────────────────────────────────────────────────────────────────────────────────────────┤ │

│  │  Sub-item 3.1: Bill of Lading Generation (DSV/Bidvest/Rhenus)                   | Day 112  | 🔴 Critical        │ │

│  │  Sub-item 3.2: Vessel Loading (Shanghai/Shenzhen/Guangzhou)                     | Day 113  | 🔴 Critical        │ │

│  │  Sub-item 3.3: Vessel Departure                                                  | Day 114  | 🔴 Critical        │ │

│  │  Sub-item 3.4: Daily Vessel GPS Position Updates (Every 3 hours)                | Days 114-149 | 🟢 Medium      │ │

│  │  Sub-item 3.5: Vessel Position Update - South China Sea                         | Day 120  | 🟢 Medium          │ │

│  │  Sub-item 3.6: Vessel Position Update - Straits of Malacca                      | Day 130  | 🟢 Medium          │ │

│  │  Sub-item 3.7: Vessel Position Update - Indian Ocean                            | Day 145  | 🟢 Medium          │ │

│  │  Sub-item 3.8: Vessel Position Update - Approaching South Africa (100nm)        | Day 148  | 🔴 Critical        │ │

│  │  Sub-item 3.9: Port Arrival - Durban (Primary) + Cape Town                     | Day 149  | 🔴 Critical        │ │

│  │  Sub-item 3.10: Port Berthing & Offloading                                      | Day 149  | 🟡 High            │ │

│  │  Sub-item 3.11: Pre-arrival Customs Documentation Submission                    | Day 145  | 🟡 High            │ │

│  │  Sub-item 3.12: SARS Customs Clearance (Duty + VAT Calculation)                | Days 150-153 | 🔴 Critical    │ │

│  │  Sub-item 3.13: Customs Release Notification                                    | Day 153  | 🔴 Critical        │ │

│  │  Sub-item 3.14: Container Dispatch to 3PL Warehouse Network                     | Day 153  | 🟡 High            │ │

│  └─────────────────────────────────────────────────────────────────────────────────────────────────────────────────┘ │

│                                                                                                                      │

│  ┌─────────────────────────────────────────────────────────────────────────────────────────────────────────────────┐ │

│  │  WAREHOUSE NETWORK RECEIPT & BREAK-BULK                                                                         │ │

│  ├─────────────────────────────────────────────────────────────────────────────────────────────────────────────────┤ │

│  │  Sub-item 4.1: JHB Primary Warehouse Receipt (500,000 capacity)                  | Day 154  | 🔴 Critical        │ │

│  │  Sub-item 4.2: CPT Secondary Warehouse Receipt (300,000 capacity)               | Day 156  | 🟡 High            │ │

│  │  Sub-item 4.3: DBN Secondary Warehouse Receipt (200,000 capacity)               | Day 157  | 🟡 High            │ │

│  │  Sub-item 4.4: PE Satellite Warehouse Receipt                                    | Day 160  | 🟢 Medium          │ │

│  │  Sub-item 4.5: EL Satellite Warehouse Receipt                                    | Day 162  | 🟢 Medium          │ │

│  │  Sub-item 4.6: PLK Satellite Warehouse Receipt                                   | Day 165  | 🟢 Medium          │ │

│  │  Sub-item 4.7: BFN Satellite Warehouse Receipt                                   | Day 168  | 🟢 Medium          │ │

│  │  Sub-item 4.8: KIM Satellite Warehouse Receipt                                   | Day 170  | 🟢 Medium          │ │

│  │  Sub-item 4.9: UPT Satellite Warehouse Receipt                                   | Day 173  | 🟢 Medium          │ │

│  │  Sub-item 4.10: RUS Satellite Warehouse Receipt                                  | Day 176  | 🟢 Medium          │ │

│  │  Sub-item 4.11: MBH Satellite Warehouse Receipt                                  | Day 179  | 🟢 Medium          │ │

│  │  Sub-item 4.12: PMB Satellite Warehouse Receipt                                  | Day 182  | 🟢 Medium          │ │

│  │  Sub-item 4.13: PCH Satellite Warehouse Receipt                                  | Day 185  | 🟢 Medium          │ │

│  │  Sub-item 4.14: MAH Satellite Warehouse Receipt                                  | Day 188  | 🟢 Medium          │ │

│  │  Sub-item 4.15: VRD Satellite Warehouse Receipt                                  | Day 191  | 🟢 Medium          │ │

│  │  Sub-item 4.16: Break-bulk & Re-palletizing by Province/District                | Days 155-200 | 🟡 High        │ │

│  └─────────────────────────────────────────────────────────────────────────────────────────────────────────────────┘ │

│                                                                                                                      │

│  ┌─────────────────────────────────────────────────────────────────────────────────────────────────────────────────┐ │

│  │  LAST-MILE DELIVERY (20,000+ Schools)                                                                           │ │

│  ├─────────────────────────────────────────────────────────────────────────────────────────────────────────────────┤ │

│  │  Sub-item 5.1: Urban Delivery (Courier Guy - 24-48h SLA)                      | Days 160-240 | 🟡 High          │ │

│  │  Sub-item 5.2: Peri-urban Delivery (Aramex - 48-72h SLA)                      | Days 165-260 | 🟡 High          │ │

│  │  Sub-item 5.3: Rural Delivery (Local Couriers - 72-120h SLA)                  | Days 170-280 | 🟡 High          │ │

│  │  Sub-item 5.4: Remote Delivery (Community Couriers - 120-168h SLA)            | Days 175-300 | 🟡 High          │ │

│  │  Sub-item 5.5: Digital POD Capture (GPS + Signature + Photo)                  | Ongoing    | 🟢 Medium          │ │

│  │  Sub-item 5.6: Real-time Status Update to Database                            | Ongoing    | 🟢 Medium          │ │

│  │  Sub-item 5.7: Exception Handling (Failed Deliveries)                         | Ongoing    | 🟡 High            │ │

│  └─────────────────────────────────────────────────────────────────────────────────────────────────────────────────┘ │

│                                                                                                                      │

└─────────────────────────────────────────────────────────────────────────────────────────────────────────────────────┘

## PART 3: COST & BUDGET MANAGEMENT

### 3.1 Budget Structure with Sub-items

yaml

BUDGET_CATEGORIES:

Production_Costs:

- Pre-press & Content Preparation: R[1,500,000]

- Paper & Materials: R[4,500,000]

- Printing & Binding (200,000 sets): R[12,000,000]

- Quality Inspection (Pre + In-process + Pre-shipment): R[500,000]

- Packing Materials (Cartons, Shrink-wrap): R[800,000]

- Palletizing & Container Loading: R[400,000]

Subtotal_Production: R[19,700,000]

Logistics_International:

- Sea Freight (55 × 40ft containers): R[4,500,000]

- Air Freight (Trainer Consignment 10,000 sets): R[1,200,000]

- Marine Insurance (All Risks): R[350,000]

- Customs Brokerage & Clearance: R[300,000]

- Import Duty (0% - Educational Materials): R[0]

- VAT (15% on CIF Value): R[3,200,000]

Subtotal_Logistics_International: R[9,550,000]

Logistics_Domestic:

- 3PL Warehouse Network (15+ locations): R[2,500,000]

- Last-Mile Delivery (20,000+ schools): R[4,200,000]

- Inter-warehouse Transfers: R[500,000]

- Inventory Management (Zoho WMS): R[300,000]

Subtotal_Logistics_Domestic: R[7,500,000]

Training_Events:

- Trainer of Trainers Program: R[800,000]

- Star Fleet Training (2,991 trainers): R[2,800,000]

- LO Teacher Workshops (10,000+ teachers): R[3,500,000]

- Venue Hire (Thusong Centres, Civic Centres): R[1,200,000]

- Catering & Refreshments: R[1,000,000]

- Training Materials & Stationery: R[500,000]

Subtotal_Training_Events: R[9,800,000]

Marketing_Branding:

- FirstRand OPCO Brand Activation: R[1,500,000]

- UCG Branded Materials & Signage: R[300,000]

- Social Media & Digital Campaigns: R[500,000]

- Photography & Videography: R[300,000]

Subtotal_Marketing_Branding: R[2,600,000]

NPO_Management:

- CareerLinx (Primary PBO) Contract: R[12,000,000]

- Regional NPO Contracts (8 partners): R[18,000,000]

Subtotal_NPO_Management: R[30,000,000]

IT_Systems:

- Zoho Suite (CRM, Inventory, Books, Creator, Flow, Analytics): R[400,000]

- Lovable.dev Web App Development: R[350,000]

- Twilio Communications Integration: R[150,000]

- API Integrations (3PL, Couriers, Maps): R[200,000]

Subtotal_IT_Systems: R[1,100,000]

Project_Management:

- Project Director & Coordinators: R[1,200,000]

- Fleet Outpost Managers (9 regions): R[2,700,000]

- Administrative Support: R[800,000]

- Travel & Accommodation: R[500,000]

Subtotal_Project_Management: R[5,200,000]

Contingency:

- 10% of Total Budget: R[8,545,000]

TOTAL_BUDGET: R[94,000,000]

### 3.2 Event-Level Cost Management

sql

-- =====================================================

-- EVENT BUDGET MANAGEMENT TABLES

-- =====================================================

CREATE TABLE event_budgets (

id UUID PRIMARY KEY DEFAULT gen_random_uuid(),

event_id UUID REFERENCES training_events(id) ON DELETE CASCADE,

budget_category VARCHAR(50) CHECK (budget_category IN ('venue', 'catering', 'materials', 'transport', 'trainer_fees', 'marketing', 'other')),

budget_item_name VARCHAR(255) NOT NULL,

budgeted_amount DECIMAL(12,2) NOT NULL,

actual_amount DECIMAL(12,2) DEFAULT 0,

variance DECIMAL(12,2) GENERATED ALWAYS AS (budgeted_amount - actual_amount) STORED,

variance_percentage DECIMAL(5,2) GENERATED ALWAYS AS (CASE WHEN budgeted_amount > 0 THEN ((budgeted_amount - actual_amount) / budgeted_amount) * 100 ELSE 0 END) STORED,

status VARCHAR(20) DEFAULT 'planned' CHECK (status IN ('planned', 'approved', 'pending_approval', 'rejected', 'paid')),

quote_document_url TEXT,

invoice_document_url TEXT,

po_number VARCHAR(100),

supplier_name VARCHAR(255),

supplier_vat_number VARCHAR(50),

approval_by UUID REFERENCES users(id),

approval_date DATE,

payment_date DATE,

payment_reference VARCHAR(100),

notes TEXT,

created_at TIMESTAMP DEFAULT NOW(),

updated_at TIMESTAMP DEFAULT NOW()

);

-- Event Budget Summary View

CREATE VIEW event_budget_summary AS

SELECT

e.id AS event_id,

e.event_name,

e.event_date,

e.province,

e.district,

SUM(eb.budgeted_amount) AS total_budgeted,

SUM(eb.actual_amount) AS total_actual,

SUM(eb.budgeted_amount - eb.actual_amount) AS total_variance,

COUNT(CASE WHEN eb.status = 'pending_approval' THEN 1 END) AS pending_approvals,

COUNT(CASE WHEN eb.status = 'approved' THEN 1 END) AS approved_items,

COUNT(CASE WHEN eb.status = 'paid' THEN 1 END) AS paid_items,

COUNT(CASE WHEN eb.status = 'rejected' THEN 1 END) AS rejected_items

FROM training_events e

LEFT JOIN event_budgets eb ON e.id = eb.event_id

GROUP BY e.id, e.event_name, e.event_date, e.province, e.district;

## PART 4: RISK MANAGEMENT & ESCALATION WORKFLOW

### 4.1 Risk Matrix Integration

yaml

Risk_ID: R-001

Category: Production

Risk_Description: Printer quality failure - substandard printing

Impact_Level: 5 (Critical)

Probability: 2 (Low)

Risk_Score: 10

Mitigation_Strategy:

- Pre-production sample approval

- In-process QC at 25%, 50%, 75% milestones

- Third-party inspection (1% sample)

- ISO 9001 audit verification

Insurance_Required:

- Liability Insurance (Printer)

- Performance Bond (10% of contract value)

Escalation_Workflow:

Level_1: Quality Inspector → Fleet Outpost Manager (Within 2 hours)

Level_2: Fleet Outpost Manager → Fleet Commander (Within 4 hours)

Level_3: Fleet Commander → Mission Control (Within 8 hours)

Level_4: Mission Control → Sponsor Orbit Control (Within 24 hours)

Recovery_Plan:

- Backup manufacturer identified

- Expedited production (overtime + subcontract)

- Partial air freight for critical volumes

- Communication to stakeholders (NPOs, DBE, FRF)

Risk_ID: R-002

Category: Logistics

Risk_Description: Container loss at sea (piracy/jettison)

Impact_Level: 5 (Critical)

Probability: 1 (Very Low)

Risk_Score: 5

Mitigation_Strategy:

- Direct routing via reputable carriers

- Real-time GPS tracking (Every 3 hours)

- Cargo insurance (110% of CIF Value)

- Bonded warehouse security

Insurance_Required:

- Marine Cargo Insurance (All Risks)

- Hull & Machinery Insurance

- Political Risk Insurance (for piracy zones)

Escalation_Workflow:

Level_1: Carrier → 3PL Logistics Coordinator (Immediate)

Level_2: 3PL → Fleet Commander (Within 1 hour)

Level_3: Fleet Commander → Mission Control (Within 2 hours)

Level_4: Mission Control → Sponsor (Within 4 hours)

Recovery_Plan:

- Immediate insurance claim process

- Backup inventory from buffer stock

- Alternative production for replacement sets

- Updated delivery schedule communicated

Risk_ID: R-003

Category: Distribution

Risk_Description: Delivery failure - School refuses/doesn't accept UCG

Impact_Level: 3 (Medium)

Probability: 3 (Medium)

Risk_Score: 9

Mitigation_Strategy:

- Pre-delivery SMS to school principal (48 hours)

- Confirmation call (24 hours)

- Principal engagement via DBE endorsement

- NPO follow-up for difficult schools

Escalation_Workflow:

Level_1: Courier → NPO Administrator (Within 2 hours)

Level_2: NPO Administrator → Fleet Outpost Manager (Within 4 hours)

Level_3: Fleet Outpost Manager → Fleet Commander (Within 24 hours)

Level_4: Fleet Commander → DBE Official (Within 48 hours)

Recovery_Plan:

- Re-delivery scheduled within 48-72 hours

- PBO Administrator contacts school

- Additional cost approved by PBO Administrator

- Automatic SMS to courier for re-delivery

- Budget adjustment via event_budgets table

### 4.2 Escalation Matrix for Delivery Failures

text

┌─────────────────────────────────────────────────────────────────────────────────────┐

│  DELIVERY FAILURE ESCALATION MATRIX                                                 │

├─────────────────────────────────────────────────────────────────────────────────────┤

│                                                                                      │

│  Level 0: Initial Report                                                            │

│  ┌─────────────────────────────────────────────────────────────────────────────────┐ │

│  │  Trigger: Courier unable to deliver (school closed, no authorized recipient)    │ │

│  │  Action: Courier uploads delivery failure reason via mobile app               │ │

│  │  Responsible: Courier Driver                                                   │ │

│  │  Timeframe: Within 15 minutes of attempt                                      │ │

│  │  System Action: Automatic log in deliveries table (status='failed')           │ │

│  │  Notification: SMS to NPO Administrator + Fleet Outpost Manager               │ │

│  └─────────────────────────────────────────────────────────────────────────────────┘ │

│                                    │                                                 │

│                                    ▼                                                 │

│  Level 1: NPO Administrator Response                                                 │

│  ┌─────────────────────────────────────────────────────────────────────────────────┐ │

│  │  Action: Review failure reason, contact school via phone                       │ │

│  │  Responsible: NPO Administrator                                                │ │

│  │  Timeframe: Within 2 hours of notification                                    │ │

│  │  System Action: Update order_allocations status to 'pending_re_delivery'      │ │

│  │  Notification: Internal note in training_events comments                      │ │

│  │  Escalation Criteria: If no response after 3 attempts → Level 2               │ │

│  └─────────────────────────────────────────────────────────────────────────────────┘ │

│                                    │                                                 │

│                                    ▼                                                 │

│  Level 2: Fleet Outpost Manager Escalation                                           │

│  ┌─────────────────────────────────────────────────────────────────────────────────┐ │

│  │  Action: Authorize re-delivery, approve additional budget                      │ │

│  │  Responsible: Fleet Outpost Manager                                            │ │

│  │  Timeframe: Within 4 hours of Level 1 escalation                               │ │

│  │  System Action: Create re-delivery order in order_allocations                 │ │

│  │  Notification: SMS to Courier Partner API (re-delivery request)               │ │

│  │  Escalation Criteria: If re-delivery fails again → Level 3                    │ │

│  │  Budget Action: Create event_budget record for extra courier cost             │ │

│  └─────────────────────────────────────────────────────────────────────────────────┘ │

│                                    │                                                 │

│                                    ▼                                                 │

│  Level 3: Fleet Commander Escalation                                                 │

│  ┌─────────────────────────────────────────────────────────────────────────────────┐ │

│  │  Action: Direct DBE intervention, consider alternate delivery method          │ │

│  │  Responsible: Fleet Commander                                                  │ │

│  │  Timeframe: Within 24 hours of Level 2 escalation                               │ │

│  │  System Action: Mark school as 'high_priority' in schools table               │ │

│  │  Notification: Email to DBE Official + Mission Control                        │ │

│  │  Escalation Criteria: If DBE intervention fails → Level 4                     │ │

│  └─────────────────────────────────────────────────────────────────────────────────┘ │

│                                    │                                                 │

│                                    ▼                                                 │

│  Level 4: Mission Control Escalation                                                 │

│  ┌─────────────────────────────────────────────────────────────────────────────────┐ │

│  │  Action: Direct intervention via DBE National Office                          │ │

│  │  Responsible: Mission Control (IBATUR)                                         │ │

│  │  Timeframe: Within 48 hours of Level 3 escalation                               │ │

│  │  System Action: Escalation report generated in kpi_tracking                   │ │

│  │  Notification: Formal letter to DBE National + Sponsor notification           │ │

│  └─────────────────────────────────────────────────────────────────────────────────┘ │

│                                                                                      │

└─────────────────────────────────────────────────────────────────────────────────────┘

## PART 5: REAL-TIME DATA PROPAGATION

### 5.1 Data Flow from China to School

text

┌─────────────────────────────────────────────────────────────────────────────────────┐

│  DATA FLOW: CHINA PRODUCTION → SCHOOL DELIVERY                                      │

├─────────────────────────────────────────────────────────────────────────────────────┤

│                                                                                      │

│  ┌─────────────────────────────────────────────────────────────────────────────────┐ │

│  │  CHINA PRODUCTION (Printer Systems)                                             │ │

│  │  ┌─────────────────────────────────────────────────────────────────────────────┐ │ │

│  │  │  Data Points:                                                              │ │ │

│  │  │  • Production Milestone %                                                  │ │ │

│  │  │  • QC Pass/Fail Status                                                     │ │ │

│  │  │  • Batch Number Assigned                                                  │ │ │

│  │  │  • Container IDs & Seals                                                  │ │ │

│  │  │  • Packing List Generation                                                │ │ │

│  │  └─────────────────────────────────────────────────────────────────────────────┘ │ │

│  │                              │                                                  │ │

│  │                              ▼                                                  │ │

│  │  ┌─────────────────────────────────────────────────────────────────────────────┐ │ │

│  │  │  REAL-TIME SYNC (Every 30 minutes via API)                                 │ │ │

│  │  │  ┌─────────────────────────────────────────────────────────────────────────┐ │ │

│  │  │  │  inventory_batches table updated                                       │ │ │

│  │  │  │  quality_inspections table updated                                     │ │ │

│  │  │  │  Push notification to stakeholders                                     │ │ │

│  │  │  └─────────────────────────────────────────────────────────────────────────┘ │ │

│  │  └─────────────────────────────────────────────────────────────────────────────┘ │ │

│  └─────────────────────────────────────────────────────────────────────────────────┘ │

│                                    │                                                 │

│                                    ▼                                                 │

│  ┌─────────────────────────────────────────────────────────────────────────────────┐ │

│  │  SHIPPING (3PL & Courier APIs)                                                  │ │

│  │  ┌─────────────────────────────────────────────────────────────────────────────┐ │ │

│  │  │  Data Points (Every 3 hours):                                              │ │ │

│  │  │  • Vessel GPS Position                                                     │ │ │

│  │  │  • Air Freight Tracking                                                    │ │ │

│  │  │  • Port Arrival ETA                                                       │ │ │

│  │  │  • Customs Clearance Status                                               │ │ │

│  │  └─────────────────────────────────────────────────────────────────────────────┘ │ │

│  │                              │                                                  │ │

│  │                              ▼                                                  │ │

│  │  ┌─────────────────────────────────────────────────────────────────────────────┐ │ │

│  │  │  REAL-TIME SYNC (Webhooks every 30 seconds)                                │ │ │

│  │  │  ┌─────────────────────────────────────────────────────────────────────────┐ │ │

│  │  │  │  inventory_batches table updated                                       │ │ │

│  │  │  │  courier_webhook_logs table updated                                    │ │ │

│  │  │  │  Delivery tracking numbers generated                                   │ │ │

│  │  │  └─────────────────────────────────────────────────────────────────────────┘ │ │

│  │  └─────────────────────────────────────────────────────────────────────────────┘ │ │

│  └─────────────────────────────────────────────────────────────────────────────────┘ │

│                                    │                                                 │

│                                    ▼                                                 │

│  ┌─────────────────────────────────────────────────────────────────────────────────┐ │

│  │  WAREHOUSE RECEIPT (3PL WMS via Extensiv API)                                   │ │

│  │  ┌─────────────────────────────────────────────────────────────────────────────┐ │ │

│  │  │  Data Points:                                                              │ │ │

│  │  │  • Warehouse Receipt Confirmation                                          │ │ │

│  │  │  • Stock Level Update                                                     │ │ │

│  │  │  • Break-bulk Progress                                                    │ │ │

│  │  │  • Re-palletizing Status                                                  │ │ │

│  │  └─────────────────────────────────────────────────────────────────────────────┘ │ │

│  │                              │                                                  │ │

│  │                              ▼                                                  │ │

│  │  ┌─────────────────────────────────────────────────────────────────────────────┐ │ │

│  │  │  REAL-TIME SYNC (REST API every 15 minutes)                                │ │ │

│  │  │  ┌─────────────────────────────────────────────────────────────────────────┐ │ │

│  │  │  │  warehouses table updated                                              │ │ │

│  │  │  │  inventory_batches table updated                                       │ │ │

│  │  │  │  Stock alerts triggered (<10% threshold)                               │ │ │

│  │  │  └─────────────────────────────────────────────────────────────────────────┘ │ │

│  │  └─────────────────────────────────────────────────────────────────────────────┘ │ │

│  └─────────────────────────────────────────────────────────────────────────────────┘ │

│                                    │                                                 │

│                                    ▼                                                 │

│  ┌─────────────────────────────────────────────────────────────────────────────────┐ │

│  │  LAST-MILE DELIVERY (Courier Systems via API)                                   │ │

│  │  ┌─────────────────────────────────────────────────────────────────────────────┐ │ │

│  │  │  Data Points:                                                              │ │ │

│  │  │  • Pick-up Confirmation                                                    │ │ │

│  │  │  • In-Transit Updates (Every 2 hours)                                     │ │ │

│  │  │  • Out-for-Delivery Notification                                           │ │ │

│  │  │  • Delivery Attempt Logs                                                  │ │ │

│  │  │  • Digital POD (GPS + Signature + Photo)                                  │ │ │

│  │  └─────────────────────────────────────────────────────────────────────────────┘ │ │

│  │                              │                                                  │ │

│  │                              ▼                                                  │ │

│  │  ┌─────────────────────────────────────────────────────────────────────────────┐ │ │

│  │  │  REAL-TIME SYNC (Mobile App + Webhooks)                                    │ │ │

│  │  │  ┌─────────────────────────────────────────────────────────────────────────┐ │ │

│  │  │  │  deliveries table updated                                              │ │ │

│  │  │  │  order_allocations status updated                                      │ │ │

│  │  │  │  schools table updated (last_visit_date, follow_up_required)           │ │ │

│  │  │  │  event_attendees updated (if delivery at training event)               │ │ │

│  │  │  └─────────────────────────────────────────────────────────────────────────┘ │ │

│  │  └─────────────────────────────────────────────────────────────────────────────┘ │ │

│  └─────────────────────────────────────────────────────────────────────────────────┘ │

│                                                                                      │

└─────────────────────────────────────────────────────────────────────────────────────┘

### 5.2 Two-Way Data Update System

sql

-- =====================================================

-- REAL-TIME UPDATE TRIGGERS

-- =====================================================

-- Trigger: When delivery status changes, update dashboard

CREATE OR REPLACE FUNCTION update_delivery_status() RETURNS TRIGGER AS $$

BEGIN

-- Update order allocation status

UPDATE order_allocations

SET status = NEW.status,

updated_at = NOW()

WHERE id = NEW.order_allocation_id;

-- Update schools last delivery date

IF NEW.status = 'delivered' THEN

UPDATE schools

SET last_visit_date = NEW.actual_delivery_date,

follow_up_required = FALSE

WHERE id = (SELECT school_id FROM order_allocations WHERE id = NEW.order_allocation_id);

END IF;

-- Insert into audit log

INSERT INTO audit_logs (user_id, action, table_name, record_id, new_values)

VALUES (NEW.delivery_person_name::UUID, 'DELIVERY_UPDATE', 'deliveries', NEW.id, row_to_json(NEW));

-- Trigger push notification via Twilio

PERFORM trigger_push_notification(NEW.id);

RETURN NEW;

END;

$$ LANGUAGE plpgsql;

CREATE TRIGGER delivery_status_update

AFTER UPDATE OF status ON deliveries

FOR EACH ROW

EXECUTE FUNCTION update_delivery_status();

-- Trigger: When KPI is updated, update dashboard summary

CREATE OR REPLACE FUNCTION update_dashboard_kpis() RETURNS TRIGGER AS $$

BEGIN

-- Update project summary views

REFRESH MATERIALIZED VIEW CONCURRENTLY project_delivery_summary;

REFRESH MATERIALIZED VIEW CONCURRENTLY project_training_summary;

REFRESH MATERIALIZED VIEW CONCURRENTLY project_financial_summary;

-- Trigger sponsor dashboard refresh

PERFORM pg_notify('dashboard_refresh', json_build_object(

'table', TG_TABLE_NAME,

'record_id', NEW.id,

'action', TG_OP

)::text);

RETURN NEW;

END;

$$ LANGUAGE plpgsql;

## PART 6: LOVABLE.DEV IMPLEMENTATION PROMPTS

### Prompt 1: Project Planning Dashboard

text

Create a comprehensive project planning dashboard that integrates with the existing IBX-CAREERS4AFRICA-SA26 system. Features required:

1. Gantt Chart View:

- Master timeline with all 6 phases and sub-items

- Color coding by phase (Pre-Launch, Production, Logistics, Distribution, Training, Monitoring)

- Critical path highlighting (red)

- Dependency arrows between items

- Progress bars for each sub-item

- Click on any sub-item to open detailed view

2. 3PL Logistics Network View:

- Interactive map showing all 15+ warehouse locations

- Container tracking with real-time GPS positions

- Live vessel tracking (every 3 hours)

- Customs clearance status

- Last-mile delivery progress by province

3. Budget Management:

- Category breakdown with actual vs budgeted

- Event-level cost tracking

- Approval workflow for expenses

- Variance analysis

4. Risk Management:

- Risk matrix with impact/probability scoring

- Escalation workflow visualization

- Active risk indicators on Gantt chart

- Mitigation plan tracking

### Prompt 2: Data Propagation System

text

Implement the real-time data propagation system that:

- Syncs with Chinese printer API (production progress)

- Integrates with 3PL APIs (DSV, DHL, M6T, Bidvest, Rhenus, Stoble, Transitex)

- Connects to courier APIs (Courier Guy, Aramex, DHL Express, FedEx)

- Updates Supabase tables in real-time

- Triggers push notifications via Twilio

- Updates all dashboard views automatically

- Provides audit trail for all updates

### Prompt 3: Escalation Workflow

text

Build the escalation workflow system that:

- Captures issues via phone/email/mobile app

- Routes to appropriate level (NPO Admin → Fleet Outpost → Fleet Commander → Mission Control)

- Tracks resolution time

- Updates budget automatically for additional costs

- Sends automatic SMS/email notifications

- Generates escalation reports for sponsor

- Integrates with risk register

### Prompt 4: Event Budget Management

text

Create the event budget management module that:

- Allows uploading of quotes (food, beverages, venue, transport, trainer fees)

- Tracks approval workflow (PBO Administrator approval)

- Links to event_budgets table

- Shows variances between budgeted and actual

- Integrates with financial reporting dashboard

- Generates PO numbers automatically

- Links to supplier database

## PART 7: INTEGRATION WITH MASTER PLAN

### 7.1 Linking to Previous Project Plan Elements

| Master Plan Element | Project Planning Tool Integration |
| --- | --- |
| China Production (Section B) | Gantt Chart Phase 2 + 3PL Sub-items |
| International Logistics (Section C) | Vessel Tracking + Customs Dashboard |
| Regional Warehousing (Section D) | Warehouse Network Map + Stock Levels |
| Local Distribution (Section F) | Last-Mile Delivery Tracking + POD |
| Trainer Program (Section J) | Event Budget Management + Training Dashboard |
| Risk Management (Section 27) | Risk Matrix + Escalation Workflow |
| KPIs (Section 29) | Real-time Dashboard Metrics |

### 7.2 Database Relationships

text

┌─────────────────────────────────────────────────────────────────────────────────────┐

│  DATABASE RELATIONSHIPS - PROJECT PLANNING TOOL                                      │

├─────────────────────────────────────────────────────────────────────────────────────┤

│                                                                                      │

│  inventory_batches ─────► quality_inspections                                       │

│          │                                                                           │

│          ▼                                                                           │

│  order_allocations ─────► deliveries ─────► delivery_attempts                       │

│          │                      │                                                    │

│          ▼                      ▼                                                    │

│  sponsor_school_mapping ──► schools ──► event_attendees                             │

│                                │                │                                    │

│                                ▼                ▼                                    │

│                         training_events ──► event_budgets                           │

│                                │                │                                    │

│                                ▼                ▼                                    │

│                         trainer_assignments ──► trainers                            │

│                                                                                      │

│  npo_organizations ──► npo_reports ──► kpi_tracking ──► contracts                  │

│                                                                                      │

│  warehouses ──► inventory_batches                                                   │

│                                                                                      │

│  courier_partners ──► deliveries ──► courier_webhook_logs                           │

│                                                                                      │

└─────────────────────────────────────────────────────────────────────────────────────┘

## READY FOR NEXT INSTRUCTION

This comprehensive project planning tool is now ready for:

- Copy into Lovable.dev using the prompts above

- Integration with existing database schemas

- Connection to 3PL APIs for real-time data

- Deployment of dashboard views for all stakeholders