# IBX-CAREERS4AFRICA-SA26

## COMPLETE RISK MATRIX WEB PAGE

### Standalone Interactive Risk Management Dashboard

## PART 1: RISK OVERVIEW DASHBOARD

### 1.1 Executive Summary View

text

┌─────────────────────────────────────────────────────────────────────────────────────┐

│  🚀 RISK MANAGEMENT COMMAND CENTER                                        [Live]    │

│  IBX-CAREERS4AFRICA-SA26                                                           │

├─────────────────────────────────────────────────────────────────────────────────────┤

│                                                                                      │

│  ┌─────────────────────────────────────────────────────────────────────────────────┐ │

│  │  RISK SUMMARY CARDS                                                             │ │

│  │  ┌─────────────┐ ┌─────────────┐ ┌─────────────┐ ┌─────────────┐              │ │

│  │  │ 🔴 CRITICAL  │ │ 🟠 HIGH     │ │ 🟡 MEDIUM   │ │ 🟢 LOW      │              │ │

│  │  │    3         │ │    7        │ │    12       │ │    8        │              │ │

│  │  │  Active      │ │  Active    │ │  Active     │ │  Active     │              │ │

│  │  └─────────────┘ └─────────────┘ └─────────────┘ └─────────────┘              │ │

│  └─────────────────────────────────────────────────────────────────────────────────┘ │

│                                                                                      │

│  ┌─────────────────────────────────────────────────────────────────────────────────┐ │

│  │  INCIDENT & ISSUES TRACKER                                                      │ │

│  │  ┌─────────────────────────────────────────────────────────────────────────────┐ │ │

│  │  │  Total Open Incidents: 24    |    Resolved Today: 5    |    Avg Resolution: │ │ │

│  │  │  4.2 hours                                                                  │ │ │

│  │  │                                                                              │ │ │

│  │  │  Pending Escalations:                                                         │ │ │

│  │  │  ┌──────────────────────────────────────────────────────────────────────────┐ │ │

│  │  │  │ Level 1: 2 | Level 2: 3 | Level 3: 1 | Level 4: 0 | Awaiting Council: 1 │ │ │

│  │  │  └──────────────────────────────────────────────────────────────────────────┘ │ │

│  │  │                                                                              │ │ │

│  │  │  Incident by Origin: External 8 | Internal 6 | Supplier 4 | Courier 6        │ │ │

│  │  └─────────────────────────────────────────────────────────────────────────────┘ │ │

│  └─────────────────────────────────────────────────────────────────────────────────┘ │

│                                                                                      │

└─────────────────────────────────────────────────────────────────────────────────────┘

## PART 2: COMPLETE RISK REGISTER

### 2.1 Risk Matrix - End-to-End Project Risks

#### Category 1: Production Risks (China Printing)

yaml

Risk_ID: R-001

Risk_Name: Printer Quality Failure - Substandard Printing

Risk_Level: 🔴 CRITICAL

Probability: 2/5

Impact: 5/5

Risk_Score: 10

Description: Printer fails to meet ISO 9001 standards - paper quality, binding, color accuracy

Affected_Project_Phase: Production

Responsible_Party: Chinese Manufacturer

Mitigation_Strategy:

- Pre-production sample approval (500 sets)

- In-process QC at 25%, 50%, 75% milestones

- Third-party inspection (1% sample = 2,000 sets)

- ISO 9001 certification audit before production

- Performance bond (10% contract value)

Insurance_Required:

- Liability Insurance (Printer)

- Performance Bond

- Product Warranty (12 months)

Escalation_Workflow:

Level_1: Quality Inspector → Fleet Outpost Manager (2 hours)

Level_2: Fleet Outpost Manager → Fleet Commander (4 hours)

Level_3: Fleet Commander → Mission Control (8 hours)

Level_4: Mission Control → Sponsor (24 hours)

Recovery_Plan:

- Backup manufacturer identified

- Expedited production (overtime + subcontract)

- Partial air freight for critical volumes

Cost_Impact: R 500,000 - R 2,000,000

KPI_Impact: Delivery timeline + 14 days

yaml

Risk_ID: R-002

Risk_Name: Production Delay - Raw Material Shortage

Risk_Level: 🟠 HIGH

Probability: 3/5

Impact: 4/5

Risk_Score: 12

Description: Paper/ink shortage or delivery delay from suppliers

Affected_Project_Phase: Production

Responsible_Party: Printer & Suppliers

Mitigation_Strategy:

- Buffer stock of paper (15% extra)

- Multiple paper suppliers identified

- Monthly supplier performance reviews

- Early warning system for shortages

Insurance_Required:

- Business Interruption Insurance

- Supplier Performance Bonds

Escalation_Workflow:

Level_1: Procurement → Fleet Outpost Manager (4 hours)

Level_2: Fleet Outpost Manager → Fleet Commander (8 hours)

Level_3: Fleet Commander → Mission Control (24 hours)

Recovery_Plan:

- Alternative paper sources (pre-qualified)

- Expedited shipping of materials

- Production schedule compression

Cost_Impact: R 200,000 - R 800,000

KPI_Impact: Production + 10 days

yaml

Risk_ID: R-003

Risk_Name: ISO Certification Non-Compliance

Risk_Level: 🟠 HIGH

Probability: 2/5

Impact: 5/5

Risk_Score: 10

Description: Printer fails ISO 9001, 14001, 45001, or printing-specific standards

Affected_Project_Phase: Production

Responsible_Party: Printer Quality Manager

Mitigation_Strategy:

- Audit printer certifications before contract

- Request certificates of compliance

- Incorporate ISO compliance into contract terms

- Allow for independent auditor inspection

Insurance_Required:

- Professional Indemnity (Printer)

- Warranty on Compliance

Escalation_Workflow:

Level_1: Compliance Officer → Fleet Commander (2 hours)

Level_2: Fleet Commander → Mission Control (8 hours)

Recovery_Plan:

- Legal recourse for breach of contract

- Alternative printer engagement

Cost_Impact: R 1,000,000 - R 5,000,000

KPI_Impact: Project cancellation risk

yaml

Risk_ID: R-004

Risk_Name: IP Theft - Content Leakage

Risk_Level: 🟠 HIGH

Probability: 1/5

Impact: 5/5

Risk_Score: 6

Description: Career guide content copied/stolen before/after printing

Affected_Project_Phase: Production/Distribution

Responsible_Party: Printer/Supply Chain

Mitigation_Strategy:

- Non-disclosure agreements with all partners

- Limited access to final content

- Watermarked digital assets

- Secure digital transfer protocol

Insurance_Required:

- Intellectual Property Insurance

- Cyber Insurance

Escalation_Workflow:

Level_1: Legal Team → Fleet Commander (2 hours)

Level_2: Fleet Commander → Mission Control (4 hours)

Recovery_Plan:

- Legal action (interdict)

- Content reset if leaked

Cost_Impact: R 5,000,000+ (reputation)

KPI_Impact: Brand trust damage

#### Category 2: International Logistics Risks

yaml

Risk_ID: R-005

Risk_Name: Container Loss at Sea - Piracy/Jettison/Sinking

Risk_Level: 🔴 CRITICAL

Probability: 1/5

Impact: 5/5

Risk_Score: 6

Description: Loss of 55 × 40ft containers during sea transit

Affected_Project_Phase: International Logistics

Responsible_Party: Carrier/Shipping Line

Mitigation_Strategy:

- Direct routing via reputable carriers

- Real-time GPS tracking (Every 3 hours)

- AIS vessel monitoring system

- A-rated marine cargo insurance (110% of CIF)

- Bonded warehouse security

Insurance_Required:

- Marine Cargo Insurance (All Risks) - 110% CIF

- Hull & Machinery Insurance

- Political Risk Insurance (piracy zones)

- SASRIA Marine Cover (if applicable)

Escalation_Workflow:

Level_1: Carrier → 3PL Logistics Coordinator (Immediate)

Level_2: 3PL → Fleet Commander (1 hour)

Level_3: Fleet Commander → Mission Control (2 hours)

Level_4: Mission Control → Sponsor (4 hours)

Recovery_Plan:

- Immediate insurance claim process

- Backup inventory from buffer stock (20,000 sets)

- Alternative production for replacement sets

- Communication to all stakeholders

Cost_Impact: R 15,000,000 - R 25,000,000

KPI_Impact: Delivery + 60-90 days

yaml

Risk_ID: R-006

Risk_Name: Container Theft - Port/Transit

Risk_Level: 🟠 HIGH

Probability: 2/5

Impact: 4/5

Risk_Score: 8

Description: Theft of containers at port or during inland transit

Affected_Project_Phase: International Logistics/Domestic Logistics

Responsible_Party: Port Authority/Courier

Mitigation_Strategy:

- Secure container seals (Bolt Seal + Cable Seal)

- GPS trackers in containers

- 24/7 security at ports

- Bonded warehouses for storage

- Security escorts for high-risk routes

Insurance_Required:

- Theft Insurance

- Goods-in-Transit Insurance

- Fidelity Guarantee

- SASRIA Transit Coupon

Escalation_Workflow:

Level_1: Security → Logistics Coordinator (1 hour)

Level_2: Logistics Coordinator → Fleet Commander (2 hours)

Level_3: Fleet Commander → Mission Control (4 hours)

Recovery_Plan:

- Insurance claim (theft)

- Replacement production

- Increased security measures

Cost_Impact: R 2,000,000 - R 10,000,000

KPI_Impact: Delivery + 30 days

yaml

Risk_ID: R-007

Risk_Name: Customs Clearance Delay/Rejection

Risk_Level: 🟠 HIGH

Probability: 3/5

Impact: 3/5

Risk_Score: 9

Description: SARS holds containers for documentation issues or inspections

Affected_Project_Phase: International Logistics

Responsible_Party: Customs Broker/SARS

Mitigation_Strategy:

- Pre-arrival documentation submission (7 days prior)

- Experienced SARS-accredited customs broker

- Proper HS Code classification (educational materials)

- Complete commercial invoices and packing lists

- Pre-clearance approval for special permits

Insurance_Required:

- Demurrage Cover

- Storage Insurance

- Customs Guarantee Bond

Escalation_Workflow:

Level_1: Customs Broker → Logistics Coordinator (2 hours)

Level_2: Logistics Coordinator → Fleet Commander (4 hours)

Level_3: Fleet Commander → SARS Senior Official (8 hours)

Recovery_Plan:

- Expedited documentation correction

- Request for priority inspection

- Temporary storage facility

- Pay demurrage/storage costs

Cost_Impact: R 100,000 - R 500,000

KPI_Impact: Delivery + 5-10 days

yaml

Risk_ID: R-008

Risk_Name: Weather-Related Marine Cargo Damage

Risk_Level: 🟡 MEDIUM

Probability: 3/5

Impact: 3/5

Risk_Score: 9

Description: Storm/rough seas damage to containers or contents

Affected_Project_Phase: International Logistics

Responsible_Party: Carrier/Weather

Mitigation_Strategy:

- Weather routing for vessels

- High-quality packaging (waterproof)

- Shock indicators on containers

- Route optimization (avoid severe weather)

Insurance_Required:

- Marine Cargo Insurance (All Risks) - including weather

- Hull Insurance (weather damage)

Escalation_Workflow:

Level_1: Carrier → Logistics Coordinator (4 hours)

Level_2: Logistics Coordinator → Fleet Commander (8 hours)

Recovery_Plan:

- Insurance claim

- Inspection at port

- Replacement for damaged goods

Cost_Impact: R 500,000 - R 3,000,000

KPI_Impact: Delivery + 5-15 days (weather waiting)

yaml

Risk_ID: R-009

Risk_Name: Air Freight Delay - Trainer Consignment

Risk_Level: 🟠 HIGH

Probability: 2/5

Impact: 4/5

Risk_Score: 8

Description: 10,000 trainer sets delayed in air freight

Affected_Project_Phase: International Logistics

Responsible_Party: DHL Global Forwarding

Mitigation_Strategy:

- Priority air freight booking

- Multiple flight options (DHL + alternatives)

- Early departure from China

- Real-time air tracking

Insurance_Required:

- Air Freight Insurance

- Delay Insurance (liquidated damages)

Escalation_Workflow:

Level_1: DHL → Logistics Coordinator (2 hours)

Level_2: Logistics Coordinator → Fleet Commander (4 hours)

Level_3: Fleet Commander → Training Manager (8 hours)

Recovery_Plan:

- Alternative flights identified

- Partial shipment from Singapore hub

- Digital training materials for initial sessions

- Rescheduling of trainer events

Cost_Impact: R 500,000 - R 1,200,000

KPI_Impact: Training start + 7 days

#### Category 3: Warehousing & Distribution Risks

yaml

Risk_ID: R-010

Risk_Name: Warehouse Fire/Structural Damage

Risk_Level: 🔴 CRITICAL

Probability: 1/5

Impact: 5/5

Risk_Score: 6

Description: Fire, flood, or structural failure at any warehouse location

Affected_Project_Phase: Warehousing

Responsible_Party: Warehouse Operator

Mitigation_Strategy:

- Fire suppression systems (sprinklers)

- 24/7 security monitoring

- Regular fire drills and inspections

- Fire-resistant construction

- Smoke/fire detection systems

Insurance_Required:

- Property All-Risk Insurance (Buildings + Contents)

- Business Interruption Insurance

- Stock Throughput Insurance

- SASRIA Fire Cover (riots/unrest)

Escalation_Workflow:

Level_1: Warehouse Manager → 3PL Director (Immediate)

Level_2: 3PL Director → Fleet Commander (1 hour)

Level_3: Fleet Commander → Mission Control (2 hours)

Level_4: Mission Control → Sponsor (4 hours)

Recovery_Plan:

- Immediate insurance claim

- Transfer stock from other warehouses

- Temporary storage facilities

- Emergency distribution plan

Cost_Impact: R 5,000,000 - R 50,000,000

KPI_Impact: Project halted for 30+ days

yaml

Risk_ID: R-011

Risk_Name: Warehouse Theft by Staff/External

Risk_Level: 🟠 HIGH

Probability: 2/5

Impact: 4/5

Risk_Score: 8

Description: Theft of UCG sets from warehouse by employees or criminals

Affected_Project_Phase: Warehousing

Responsible_Party: Warehouse Operator

Mitigation_Strategy:

- 24/7 CCTV surveillance

- Access control systems (biometric)

- Background checks for all staff

- Inventory cycle counts (weekly)

- Random spot checks

Insurance_Required:

- Fidelity Guarantee Insurance

- Crime Insurance

- Stock Theft Insurance

- SASRIA Cover (if unrest-related)

Escalation_Workflow:

Level_1: Security → Warehouse Manager (1 hour)

Level_2: Warehouse Manager → Fleet Commander (2 hours)

Level_3: Fleet Commander → SAPS/Police (4 hours)

Recovery_Plan:

- Police investigation

- Insurance claim

- Enhanced security measures

- Staff rotation/suspension

Cost_Impact: R 100,000 - R 500,000

KPI_Impact: Inventory variance + stock loss

yaml

Risk_ID: R-012

Risk_Name: Inventory Mismatch/Loss

Risk_Level: 🟡 MEDIUM

Probability: 3/5

Impact: 3/5

Risk_Score: 9

Description: Mismatch between system stock and physical stock

Affected_Project_Phase: Warehousing

Responsible_Party: Warehouse Manager/Inventory Clerk

Mitigation_Strategy:

- Barcode scanning for all movements

- Weekly cycle counts

- Month-end stock reconciliation

- Zoho Inventory WMS system

- Dual verification for high-value items

Insurance_Required:

- Stock Throughput Insurance

- Fidelity Guarantee

Escalation_Workflow:

Level_1: Inventory Clerk → Warehouse Manager (4 hours)

Level_2: Warehouse Manager → Fleet Commander (8 hours)

Recovery_Plan:

- Full stock take

- Investigate discrepancies

- System correction

- Staff disciplinary action

Cost_Impact: R 50,000 - R 300,000

KPI_Impact: Inventory accuracy <98%

yaml

Risk_ID: R-013

Risk_Name: Inter-Warehouse Transfer Delay/Loss

Risk_Level: 🟡 MEDIUM

Probability: 3/5

Impact: 2/5

Risk_Score: 6

Description: Goods lost or delayed between warehouses

Affected_Project_Phase: Warehousing/Distribution

Responsible_Party: Courier/3PL

Mitigation_Strategy:

- GPS tracking on all transfers

- Insurance for transfers

- Route optimization

- Time-specific SLAs

Insurance_Required:

- Goods-in-Transit Insurance

- Stock Throughput Insurance

Escalation_Workflow:

Level_1: Courier → Logistics Coordinator (4 hours)

Level_2: Logistics Coordinator → Fleet Commander (8 hours)

Recovery_Plan:

- Insurance claim

- Alternative stock allocation

- Expedited transfer

Cost_Impact: R 20,000 - R 100,000

KPI_Impact: Stock imbalance + 2 days

#### Category 4: Last-Mile Delivery Risks

yaml

Risk_ID: R-014

Risk_Name: Delivery Failure - School Refuses/Doesn't Accept

Risk_Level: 🟡 MEDIUM

Probability: 3/5

Impact: 3/5

Risk_Score: 9

Description: School refuses delivery (no staff, no authorized person)

Affected_Project_Phase: Distribution

Responsible_Party: Courier/School

Mitigation_Strategy:

- Pre-delivery SMS to principal (48 hours)

- Confirmation call (24 hours)

- DBE endorsement letters

- NPO follow-up for difficult schools

- WhatsApp communication group

Insurance_Required:

- Carrier Liability (SLA terms)

Escalation_Workflow:

Level_1: Courier → NPO Administrator (2 hours)

Level_2: NPO Administrator → Fleet Outpost Manager (4 hours)

Level_3: Fleet Outpost → DBE Official (24 hours)

Level_4: DBE → School Principal (48 hours)

Recovery_Plan:

- Re-delivery scheduled within 48-72 hours

- PBO Administrator contacts school

- Additional cost approved by PBO Administrator

- Automatic SMS to courier for re-delivery

- Budget adjustment in event_budgets table

Cost_Impact: R 150 - R 200 per re-delivery

KPI_Impact: On-time delivery rate -2%

yaml

Risk_ID: R-015

Risk_Name: Courier Theft/Hijacking During Delivery

Risk_Level: 🟠 HIGH

Probability: 2/5

Impact: 4/5

Risk_Score: 8

Description: Goods stolen from courier during delivery

Affected_Project_Phase: Distribution

Responsible_Party: Courier

Mitigation_Strategy:

- GPS tracking on vehicles

- Tamper-evident packaging

- Courier vetting (background checks)

- High-risk route security measures

- Two-person delivery in high-risk areas

Insurance_Required:

- Goods-in-Transit Insurance

- Theft Insurance

- Carrier Liability

Escalation_Workflow:

Level_1: Courier → Logistics Coordinator (1 hour)

Level_2: Logistics Coordinator → Fleet Commander (2 hours)

Level_3: Fleet Commander → SAPS (4 hours)

Recovery_Plan:

- Police case opened

- Insurance claim

- Re-delivery from warehouse

Cost_Impact: R 500 - R 5,000 per incident

KPI_Impact: Delivery success rate -3%

yaml

Risk_ID: R-016

Risk_Name: Damaged Goods During Last-Mile Delivery

Risk_Level: 🟡 MEDIUM

Probability: 4/5

Impact: 2/5

Risk_Score: 8

Description: Goods damaged during handling, loading, or transit

Affected_Project_Phase: Distribution

Responsible_Party: Courier

Mitigation_Strategy:

- Reinforced packaging

- Handling training for couriers

- Shock indicators on packages

- "Fragile" labeling

- Palletized delivery where possible

Insurance_Required:

- Carrier Liability (SLA terms)

- Goods-in-Transit Insurance

Escalation_Workflow:

Level_1: Courier → NPO Administrator (4 hours)

Level_2: NPO Administrator → Fleet Commander (8 hours)

Recovery_Plan:

- Inspection of damaged goods

- Partial refund or replacement

- Insurance claim

- Process improvement

Cost_Impact: R 50 - R 500 per package

KPI_Impact: Damage rate +2%

yaml

Risk_ID: R-017

Risk_Name: Incorrect Delivery Address/School

Risk_Level: 🟢 LOW

Probability: 3/5

Impact: 2/5

Risk_Score: 6

Description: Delivery to wrong address or incorrect school

Affected_Project_Phase: Distribution

Responsible_Party: School Data Team

Mitigation_Strategy:

- Address verification before dispatch

- GPS coordinates in school database

- Recipient ID verification (last 4 digits)

- Double-checking with school principal

- Geocoding validation

Insurance_Required:

- Professional Indemnity

Escalation_Workflow:

Level_1: Courier → NPO Administrator (4 hours)

Level_2: NPO Administrator → Fleet Commander (8 hours)

Recovery_Plan:

- Recovery of goods

- Correct delivery re-scheduled

- Database correction

Cost_Impact: R 150 - R 300 per incident

KPI_Impact: Delivery accuracy -1%

#### Category 5: Training & Event Risks

yaml

Risk_ID: R-018

Risk_Name: Low Teacher Attendance at Training Events

Risk_Level: 🟡 MEDIUM

Probability: 3/5

Impact: 3/5

Risk_Score: 9

Description: Expected teachers don't attend training events

Affected_Project_Phase: Training

Responsible_Party: NPO/DBE

Mitigation_Strategy:

- DBE formal endorsement of events

- Principal engagement (direct communication)

- SMS/WhatsApp reminders (24h, 1h)

- Incentives for attendance (CPD points)

- Follow-up calls for non-registrants

Insurance_Required:

- Event Cancellation Cover

Escalation_Workflow:

Level_1: NPO Administrator → Fleet Outpost Manager (2 hours)

Level_2: Fleet Outpost → DBE Official (4 hours)

Level_3: DBE → Principal (8 hours)

Recovery_Plan:

- Reschedule event

- Virtual training option

- Mini-training sessions

- Make-up sessions

Cost_Impact: R 5,000 - R 20,000 per event

KPI_Impact: Training coverage -10%

yaml

Risk_ID: R-019

Risk_Name: Venue Unavailability/Cancellation

Risk_Level: 🟢 LOW

Probability: 2/5

Impact: 2/5

Risk_Score: 4

Description: Training venue cancels or becomes unavailable

Affected_Project_Phase: Training

Responsible_Party: Venue Provider

Mitigation_Strategy:

- Multiple venue options per district

- Backup venue pre-booked

- Venue contract with cancellation clauses

- Regular venue check-ins

Insurance_Required:

- Event Cancellation Insurance

Escalation_Workflow:

Level_1: NPO Administrator → Fleet Outpost Manager (2 hours)

Level_2: Fleet Outpost → Alternative Venue (4 hours)

Recovery_Plan:

- Move to backup venue

- Notify all attendees

- Reschedule if necessary

Cost_Impact: R 1,000 - R 5,000 per incident

KPI_Impact: Event cancellation rate <2%

yaml

Risk_ID: R-020

Risk_Name: Trainer Unavailability/No-Show

Risk_Level: 🟡 MEDIUM

Probability: 2/5

Impact: 3/5

Risk_Score: 6

Description: Star Fleet trainer doesn't show up for training

Affected_Project_Phase: Training

Responsible_Party: Trainer

Mitigation_Strategy:

- Backup trainers identified per province

- Cross-province deployment capability

- Trainer call schedule (24h confirmation)

- Trainer contract with availability clauses

- Emergency trainer list

Insurance_Required:

- Professional Indemnity (Trainer)

Escalation_Workflow:

Level_1: NPO Administrator → Fleet Outpost Manager (2 hours)

Level_2: Fleet Outpost → Backup Trainer (4 hours)

Recovery_Plan:

- Deploy backup trainer

- Reschedule session

- Virtual training option

- Trainer disciplinary action

Cost_Impact: R 2,000 - R 10,000 per incident

KPI_Impact: Training quality -5%

#### Category 6: Financial & Budget Risks

yaml

Risk_ID: R-021

Risk_Name: Currency Fluctuation (ZAR vs CNY/USD)

Risk_Level: 🟡 MEDIUM

Probability: 4/5

Impact: 3/5

Risk_Score: 12

Description: ZAR weakens against CNY/USD, increasing costs

Affected_Project_Phase: Production/Logistics

Responsible_Party: Finance/Procurement

Mitigation_Strategy:

- Forward exchange contracts

- Pricing in ZAR where possible

- Cost buffer for currency fluctuations

- Regular currency monitoring

Insurance_Required:

- Currency Hedging

- Currency Risk Insurance

Escalation_Workflow:

Level_1: Finance → Fleet Commander (Monthly)

Level_2: Fleet Commander → Mission Control (Monthly)

Recovery_Plan:

- Adjust budget allocation

- Cost reduction in other areas

- Re-negotiate supplier pricing

Cost_Impact: R 500,000 - R 2,000,000

KPI_Impact: Budget variance +5-10%

yaml

Risk_ID: R-022

Risk_Name: Sponsor Payment Delay/Default

Risk_Level: 🔴 CRITICAL

Probability: 1/5

Impact: 5/5

Risk_Score: 6

Description: FirstRand Foundation payment delayed or defaulted

Affected_Project_Phase: All Phases

Responsible_Party: Sponsor

Mitigation_Strategy:

- Deposit structure (80% upfront)

- Clear payment schedule in contract

- Monthly financial reporting to sponsor

- Good relationship management

- Progress milestones tied to payments

Insurance_Required:

- Credit Insurance

- Political Risk Insurance

Escalation_Workflow:

Level_1: Finance → Mission Control (Immediate)

Level_2: Mission Control → Sponsor (24 hours)

Recovery_Plan:

- Draw on contingency

- Bridge financing

- Project scope adjustment

- Payment renegotiation

Cost_Impact: R 10,000,000 - R 90,000,000

KPI_Impact: Project halt

yaml

Risk_ID: R-023

Risk_Name: Budget Overrun - Event Costs

Risk_Level: 🟡 MEDIUM

Probability: 3/5

Impact: 2/5

Risk_Score: 6

Description: Event costs exceed budgeted amounts

Affected_Project_Phase: Training/Events

Responsible_Party: NPO/Event Organizer

Mitigation_Strategy:

- Strict budget approval process

- Quote comparison for all expenses

- Variance tracking dashboard

- 10% contingency per event

- Approval required for changes

Insurance_Required:

- None

Escalation_Workflow:

Level_1: NPO → Fleet Outpost Manager (4 hours)

Level_2: Fleet Outpost → Fleet Commander (8 hours)

Recovery_Plan:

- Re-allocate from less used categories

- Reduce non-essential costs

- Use contingency

Cost_Impact: R 2,000 - R 20,000 per event

KPI_Impact: Budget compliance -2%

#### Category 7: Legal & Compliance Risks

yaml

Risk_ID: R-024

Risk_Name: Contractual Dispute - Printer/Courier

Risk_Level: 🟡 MEDIUM

Probability: 2/5

Impact: 4/5

Risk_Score: 8

Description: Dispute over SLA terms, quality, or payment

Affected_Project_Phase: Production/Logistics

Responsible_Party: Legal/Procurement

Mitigation_Strategy:

- Clear SLA terms in all contracts

- Chinese legal advice for printer contract

- Arbitration clauses in contracts

- Regular contract compliance reviews

Insurance_Required:

- Legal Expenses Insurance

- Professional Indemnity

Escalation_Workflow:

Level_1: Legal → Fleet Commander (4 hours)

Level_2: Fleet Commander → Mission Control (8 hours)

Level_3: Mission Control → Arbitrator (24 hours)

Recovery_Plan:

- Mediation

- Arbitration

- Alternate supplier engagement

Cost_Impact: R 100,000 - R 1,000,000

KPI_Impact: Project delay + 30 days

yaml

Risk_ID: R-025

Risk_Name: IP/Content Ownership Dispute

Risk_Level: 🟠 HIGH

Probability: 1/5

Impact: 5/5

Risk_Score: 6

Description: Dispute over content ownership in career guides

Affected_Project_Phase: Pre-Launch/Production

Responsible_Party: Content Team/Legal

Mitigation_Strategy:

- Clear IP ownership contracts

- Original content creation

- Proper copyright notices

- Content review process

- Legal sign-off on all content

Insurance_Required:

- Intellectual Property Insurance

- Professional Indemnity (Content)

- Media/Publishers Liability (E&O)

Escalation_Workflow:

Level_1: Content Team → Fleet Commander (4 hours)

Level_2: Fleet Commander → Legal (8 hours)

Level_3: Legal → Mission Control (24 hours)

Recovery_Plan:

- Content modification

- Licensing agreement

- Legal action if necessary

Cost_Impact: R 500,000 - R 10,000,000

KPI_Impact: Brand reputation damage

yaml

Risk_ID: R-026

Risk_Name: Defamation/Libel in Content

Risk_Level: 🟠 HIGH

Probability: 1/5

Impact: 5/5

Risk_Score: 6

Description: Content contains defamatory statements about individuals/organizations

Affected_Project_Phase: Pre-Launch/Production

Responsible_Party: Content Team

Mitigation_Strategy:

- Legal review of all content

- Multiple editorial review stages

- Clear content guidelines

- Subject matter expert reviews

- Feedback mechanism for corrections

Insurance_Required:

- Media Liability Insurance (Publishers E&O)

- Professional Indemnity

- Cyber Insurance

Escalation_Workflow:

Level_1: Content Team → Legal (2 hours)

Level_2: Legal → Fleet Commander (4 hours)

Level_3: Fleet Commander → Mission Control (8 hours)

Recovery_Plan:

- Content correction/removal

- Public apology if needed

- Legal defense

- Insurance claim

Cost_Impact: R 1,000,000 - R 20,000,000

KPI_Impact: Brand reputation damage

#### Category 8: External & Force Majeure Risks

yaml

Risk_ID: R-027

Risk_Name: Political Unrest/Riots - SASRIA Incident

Risk_Level: 🟠 HIGH

Probability: 2/5

Impact: 4/5

Risk_Score: 8

Description: Riots, strikes, protests damaging assets or disrupting operations

Affected_Project_Phase: All Phases

Responsible_Party: External

Mitigation_Strategy:

- SASRIA Insurance cover added to all policies

- Security assessments for high-risk areas

- Business continuity plans

- Alternative routes identified

- Remote operations capability

Insurance_Required:

- SASRIA Cover (Material Damage + Business Interruption)

- Political Risk Insurance

- Business Interruption Insurance

Escalation_Workflow:

Level_1: Operations → Fleet Commander (Immediate)

Level_2: Fleet Commander → Mission Control (1 hour)

Level_3: Mission Control → Sponsor (2 hours)

Level_4: Mission Control → SASRIA (4 hours)

Recovery_Plan:

- Activate business continuity plan

- Insurance claim (SASRIA)

- Temporary relocation of operations

- Alternative logistics routes

- Staff safety protocols

Cost_Impact: R 1,000,000 - R 50,000,000

KPI_Impact: Project halt + 30+ days

yaml

Risk_ID: R-028

Risk_Name: Disease Outbreak/Pandemic Restrictions

Risk_Level: 🟡 MEDIUM

Probability: 2/5

Impact: 3/5

Risk_Score: 6

Description: COVID-19 or other disease outbreak restrictions

Affected_Project_Phase: All Phases

Responsible_Party: External

Mitigation_Strategy:

- Virtual training options (Zoom/Teams)

- Remote delivery protocols

- Digital content distribution

- Social distancing at events (if allowed)

- Hybrid event model

Insurance_Required:

- Business Interruption Insurance

- Event Cancellation Insurance

Escalation_Workflow:

Level_1: Operations → Fleet Commander (4 hours)

Level_2: Fleet Commander → Mission Control (8 hours)

Recovery_Plan:

- Shift to virtual training

- Postal/digital delivery

- Extended project timeline

Cost_Impact: R 500,000 - R 5,000,000

KPI_Impact: Training completion +30 days

yaml

Risk_ID: R-029

Risk_Name: Load Shedding/Eskom Power Outages

Risk_Level: 🟡 MEDIUM

Probability: 5/5

Impact: 2/5

Risk_Score: 10

Description: Eskom load shedding affects warehouse/office operations

Affected_Project_Phase: Warehousing/Office

Responsible_Party: Eskom/External

Mitigation_Strategy:

- UPS/Generator backup for critical systems

- Solar power for warehouses

- Load shedding schedules monitoring

- Offline data backup

- Alternative work arrangements

Insurance_Required:

- Business Interruption Insurance

- Electronic Equipment Insurance

Escalation_Workflow:

Level_1: Operations → Fleet Commander (4 hours)

Level_2: Fleet Commander → Mission Control (8 hours)

Recovery_Plan:

- Generator activation

- Offline processing

- Rescheduled activities

Cost_Impact: R 10,000 - R 50,000 per month

KPI_Impact: System downtime +2%

#### Category 9: Technology & Data Risks

yaml

Risk_ID: R-030

Risk_Name: System Downtime - Lovable/Zoho

Risk_Level: 🟡 MEDIUM

Probability: 2/5

Impact: 3/5

Risk_Score: 6

Description: Lovable.dev or Zoho systems are down

Affected_Project_Phase: All Phases (System-dependent)

Responsible_Party: IT/Cloud Provider

Mitigation_Strategy:

- Regular system backups (24-hour)

- Manual fallback procedures

- Redundant systems (Zoho + Lovable)

- Uptime monitoring (99.9% target)

- Disaster recovery plan

Insurance_Required:

- Cyber Insurance

- Business Interruption Insurance

Escalation_Workflow:

Level_1: IT → Fleet Commander (1 hour)

Level_2: Fleet Commander → Mission Control (2 hours)

Level_3: Mission Control → Service Provider (4 hours)

Recovery_Plan:

- Activate manual procedures

- Escalate to Zoho/Lovable support

- System restore from backup

Cost_Impact: R 50,000 - R 200,000 per day

KPI_Impact: Data sync lag >15 minutes

yaml

Risk_ID: R-031

Risk_Name: Data Breach/Cyber Attack

Risk_Level: 🟠 HIGH

Probability: 2/5

Impact: 4/5

Risk_Score: 8

Description: Hackers access school/personal data

Affected_Project_Phase: All Phases (System-dependent)

Responsible_Party: IT/Security

Mitigation_Strategy:

- End-to-end encryption

- Role-based access control

- Regular security assessments

- Penetration testing (quarterly)

- POPIA/GDPR compliance

- Employee security training

Insurance_Required:

- Cyber Insurance

- Data Breach Insurance

- Professional Indemnity

Escalation_Workflow:

Level_1: IT Security → Fleet Commander (1 hour)

Level_2: Fleet Commander → Mission Control (2 hours)

Level_3: Mission Control → POPIA (24 hours)

Recovery_Plan:

- Isolate breach

- Notify affected parties

- Forensic investigation

- Legal action if needed

- Insurance claim

Cost_Impact: R 500,000 - R 5,000,000

KPI_Impact: Brand reputation damage

## PART 3: INSURANCE & ASSURANCE COVERAGE MATRIX

### 3.1 Comprehensive Insurance Requirements

| Insurance Type | Coverage Amount | Provider Type | Estimated Premium | Applicable Risks |
| --- | --- | --- | --- | --- |
| Marine Cargo Insurance (All Risks) | 110% of CIF Value | International (Lloyd's, AIG, Allianz, AXA XL) | 0.5-1% of CIF | R-005, R-008 |
| Goods-in-Transit (Domestic) | Full Replacement Value | South African (Santam, Hollard, OUTsurance) | 1-2% of consignment | R-006, R-013, R-015, R-016 |
| SASRIA Cover | R500M-R1B | SASRIA SOC Ltd | R500 min annual | R-027, R-010, R-006 |
| SASRIA Transit Coupon | Per declaration | SASRIA via broker | 0.0017-0.034% of value | R-006, R-027 |
| Stock Throughput Insurance | Annual Turnover | South African | 0.75-1.5% turnover | R-010, R-011, R-012 |
| Property All-Risk | Building + Contents | South African | Based on value | R-010 |
| Business Interruption | 12 months gross profit | South African | 10-20% property premium | R-010, R-022, R-027, R-028 |
| Public Liability | R20M minimum | South African | R15,000-30,000/year | General |
| Media Liability (Publishers E&O) | R5M-R10M | International (Chubb, AXA XL) | R100,000-300,000/year | R-004, R-025, R-026 |
| Professional Indemnity | R5M | South African | R10,000-25,000/year | R-003, R-020, R-024 |
| Fidelity Guarantee | R5M | South African | R5,000-15,000/year | R-006, R-011, R-012 |
| Cyber Insurance | R10M | International/SA | R50,000-150,000/year | R-004, R-030, R-031 |
| Political Risk Insurance | Full cargo value | International | 0.2-1% cargo value | R-005, R-027 |
| Credit Insurance | 90% of receivables | South African | 0.5-1.5% insured | R-022 |
| Event Cancellation | Per event value | South African | 5-10% premium | R-018, R-019, R-028 |
| Electronic Equipment | Replacement value | South African | 2-4% of value | R-029 |

### 3.2 Recommended Insurance Providers

yaml

International_Insurers:

- AIG: Marine cargo, Cyber, Media Liability, Political Risk

- Allianz: Corporate property, Liability, Cyber, Marine

- AXA XL: Marine cargo, Media Liability, Professional Indemnity

- Chubb: MediaGuard (content risks), Property, Liability

- Lloyd's: Specialized marine cargo, Political risk (via brokers)

South_African_Insurers:

- Santam: Commercial property, Goods-in-transit, Business Interruption, Fleet

- Hollard: Business insurance, Specialist risks (iTOO), Liability

- Old Mutual Insure: Commercial packages, Liability

- OUTsurance: Goods-in-transit, Liability, Property

- Discovery Insure: Commercial packages, Social Media/Multimedia Liability [citation:5]

- Bryte Insurance: Specialized covers

- Guardrisk: Specialized covers

Brokers_and_Platforms:

- Bi-me: Digital broker for Broadcasting & Publishing [citation:1]

- Marsh SA: Lloyd's broker

- Aon South Africa: Full-service broker

- Mont Blanc Financial Services: Commercial insurance [citation:6][citation:7]

Special_Risk:

- SASRIA SOC Ltd: Riot, Strike, Public Disorder (Mandatory) [citation:2][citation:6][citation:9]

- SASRIA Transit Coupon: Transit risks during unrest [citation:10]

## PART 4: RISK MINIMAP - CLICKABLE INTERACTIVE VIEW

### 4.1 Visual Risk Mindmap

text

┌─────────────────────────────────────────────────────────────────────────────────────┐

│                        🚀 RISK COMMAND CENTER                                      │

│                        End-to-End Risk Management Mindmap                          │

├─────────────────────────────────────────────────────────────────────────────────────┤

│                                                                                      │

│                              ┌────────────────────────┐                             │

│                              │  🔴 CRITICAL RISKS     │                             │

│                              │  (3 Active)            │                             │

│                              │  • R-001: Quality     │                             │

│                              │  • R-005: Container   │                             │

│                              │  • R-010: Warehouse   │                             │

│                              │  • R-022: Payment     │                             │

│                              └───────────┬────────────┘                             │

│                                          │                                           │

│         ┌────────────────────────────────┼────────────────────────────────┐         │

│         │                                │                                │         │

│         ▼                                ▼                                ▼         │

│  ┌──────────────────┐           ┌──────────────────┐           ┌──────────────────┐ │

│  │  🏭 PRODUCTION   │           │  🚢 LOGISTICS    │           │  📦 DISTRIBUTION  │ │

│  │  Risks (4)       │           │  Risks (5)       │           │  Risks (4)        │ │

│  ├──────────────────┤           ├──────────────────┤           ├──────────────────┤ │

│  │ 🟠 R-001 Quality│           │ 🔴 R-005: Loss   │           │ 🟡 R-014: Refuse │ │

│  │ 🟠 R-002 Delay  │           │ 🟠 R-006: Theft  │           │ 🟠 R-015: Theft  │ │

│  │ 🟠 R-003 ISO    │           │ 🟠 R-007 Customs │           │ 🟡 R-016 Damage  │ │

│  │ 🟠 R-004 IP     │           │ 🟡 R-008 Weather │           │ 🟢 R-017 Address │ │

│  │                 │           │ 🟠 R-009 Air     │           │                  │ │

│  └──────────────────┘           └──────────────────┘           └──────────────────┘ │

│         │                                │                                │         │

│         └────────────────────────────────┼────────────────────────────────┘         │

│                                          │                                           │

│         ┌────────────────────────────────┼────────────────────────────────┐         │

│         │                                │                                │         │

│         ▼                                ▼                                ▼         │

│  ┌──────────────────┐           ┌──────────────────┐           ┌──────────────────┐ │

│  │  🏪 WAREHOUSE    │           │  📚 TRAINING     │           │  💰 FINANCIAL    │ │

│  │  Risks (4)       │           │  Risks (3)       │           │  Risks (2)       │ │

│  ├──────────────────┤           ├──────────────────┤           ├──────────────────┤ │

│  │ 🔴 R-010: Fire  │           │ 🟡 R-018 Attend  │           │ 🟡 R-021: FX     │ │

│  │ 🟠 R-011: Theft │           │ 🟢 R-019 Venue   │           │ 🔴 R-022 Payment │ │

│  │ 🟡 R-012: Stock │           │ 🟡 R-020 Trainer │           │                  │ │

│  │ 🟡 R-013: Xfer  │           │                  │           │                  │ │

│  └──────────────────┘           └──────────────────┘           └──────────────────┘ │

│                                                                                      │

│         ┌────────────────────────────────┼────────────────────────────────┐         │

│         │                                │                                │         │

│         ▼                                ▼                                ▼         │

│  ┌──────────────────┐           ┌──────────────────┐           ┌──────────────────┐ │

│  │  ⚖️ LEGAL        │           │  🌍 EXTERNAL     │           │  💻 TECHNOLOGY   │ │

│  │  Risks (3)       │           │  Risks (3)       │           │  Risks (2)       │ │

│  ├──────────────────┤           ├──────────────────┤           ├──────────────────┤ │

│  │ 🟡 R-024: Dispute│           │ 🟠 R-027: Unrest │           │ 🟡 R-030: System │ │

│  │ 🟠 R-025: IP     │           │ 🟡 R-028: Disease│           │ 🟠 R-031: Cyber  │ │

│  │ 🟠 R-026: Libel  │           │ 🟡 R-029: Power  │           │                  │ │

│  └──────────────────┘           └──────────────────┘           └──────────────────┘ │

│                                                                                      │

│                                          │                                           │

│                              ┌───────────▼────────────┐                             │

│                              │  🛡️ RISK COVERAGE     │                             │

│                              │  Insurance Matrix      │                             │

│                              │  • Marine Cargo       │                             │

│                              │  • SASRIA [citation:2]│                             │

│                              │  • Media Liability   │                             │

│                              │  • Goods-in-Transit  │                             │

│                              └───────────────────────┘                             │

│                                                                                      │

└─────────────────────────────────────────────────────────────────────────────────────┘

## PART 5: LOVABLE.DEV IMPLEMENTATION PROMPTS

### Prompt 1: Risk Dashboard

text

Create a standalone risk management page with the following components:

1. Executive summary cards showing risk counts by priority (Critical/High/Medium/Low)

2. Incident tracker with open/resolved counts

3. Escalation status (Level 1-4 + Awaiting Council)

4. Incident origin breakdown (External/Internal/Supplier/Courier)

5. Complete risk register table with all 31+ risks

6. Clickable risk entries that open detailed risk popups

7. Interactive risk mindmap showing relationships between risk categories

### Prompt 2: Risk Detail Popup

text

When a user clicks on any risk in the register or mindmap, display a popup with:

- Risk ID, name, and level (color-coded)

- Probability and Impact scores

- Full description

- Affected project phase

- Responsible party

- Mitigation strategy (bullet points)

- Insurance required

- Escalation workflow (4 levels)

- Recovery plan

- Cost impact estimate

- KPI impact

- Status update button

### Prompt 3: Insurance Matrix

text

Create an interactive insurance coverage matrix showing:

- All 16+ insurance types

- Coverage amounts

- Provider types (International/SA/Special Risk)

- Estimated premiums

- Applicable risks (mapped to risk IDs)

- Recommended providers with contact details

- SASRIA cover explanation [citation:2][citation:6][citation:9]

- Media Liability (Publishers E&O) explanation [citation:1][citation:5]

- Goods-in-Transit vs Marine Cargo comparison [citation:7]

### Prompt 4: Escalation Workflow

text

Build a visual escalation workflow showing:

- 4 escalation levels with timeframes

- Trigger conditions for each level

- Responsible parties at each level

- Notification flow (who gets notified when)

- Recovery steps for each level

- Integration with Twilio for automatic notifications

- Link to budget management for cost approvals

### Prompt 5: Risk Reporting

text

Create a reporting module for risk management:

- Generate risk matrix report for sponsor

- Export risk register to PDF/Excel

- Risk heat map visualization

- Risk trend over time (weekly/monthly)

- Incident resolution time tracking

- Insurance coverage gap analysis

- SASRIA compliance report [citation:2][citation:6][citation:9]

- POPIA/GDPR compliance report

## PART 6: STAKEHOLDER PORTAL ACCESS

### 6.1 Role-Based Risk Views

yaml

Sponsor_View (FirstRand Foundation):

- Executive summary (all risk levels)

- Critical risk notifications

- Insurance coverage summary

- Escalation status (Level 3-4 only)

- Budget impact of risks

- SASRIA cover status [citation:2]

- Media liability coverage [citation:1][citation:5]

Project_Manager_View:

- Complete risk register

- Incident management

- Escalation workflow (all levels)

- Budget approval for risk mitigation

- Insurance claims management

- SASRIA claims process [citation:6]

NPO_Administrator_View:

- Delivery-related risks (R-014 to R-017)

- Training-related risks (R-018 to R-020)

- Incident reporting

- Budget management for events

Service_Agent_View:

- Incident capture

- Issue resolution tracking

- Escalation initiation

- Communication management

Risk_Officer_View:

- Complete risk register management

- Risk assessment and scoring

- Insurance policy management

- Compliance monitoring (POPIA, SASRIA)

- Third-party claims management

- Audit trail

## COMPLETE RISK COVERAGE SUMMARY

| Risk Category | # Risks | Critical | High | Medium | Low | Insurance Required |
| --- | --- | --- | --- | --- | --- | --- |
| Production | 4 | 0 | 4 | 0 | 0 | Marine Cargo, Liability, Performance Bond, IP, Cyber |
| International Logistics | 5 | 1 | 3 | 1 | 0 | Marine Cargo, Goods-in-Transit, SASRIA, Political Risk |
| Warehousing | 4 | 1 | 1 | 2 | 0 | Property All-Risk, Fidelity, Stock Throughput, SASRIA |
| Distribution | 4 | 0 | 1 | 2 | 1 | Goods-in-Transit, Carrier Liability, Theft |
| Training | 3 | 0 | 0 | 2 | 1 | Event Cancellation, Professional Indemnity |
| Financial | 2 | 1 | 0 | 1 | 0 | Credit, Currency Hedge |
| Legal | 3 | 0 | 2 | 1 | 0 | Media Liability , Professional Indemnity, IP |
| External | 3 | 0 | 1 | 2 | 0 | SASRIA , Business Interruption |
| Technology | 2 | 0 | 1 | 1 | 0 | Cyber, Business Interruption |
| TOTAL | 30 | 3 | 13 | 12 | 2 | 16+ Insurance Types |

## READY FOR IMPLEMENTATION

This complete risk matrix page is now ready for:

- Copy into Lovable.dev using the prompts above

- Integration with existing database (risk_register table)

- Connection to Twilio for escalation notifications

- Link to budget management for cost approval workflows

- SASRIA cover integration for unrest-related risks

- Media liability cover integration for content risks

- Goods-in-Transit integration for logistics risks

The risk management page provides end-to-end coverage from manufacturing to Direct-to-School delivery, with full escalation and insurance integration.